## Introduction
Barrel Modules Status
Version history | date (yyyy/mm/dd)
1st version | 2003-07-03
1.1 | 2003-07-24
1.2 | 2003-07-29 | updates in Inventory, Pipeline, forB5B6, HOLD, REWORK, s-curves sheets
1.3 | 2003-07-31 | update in Pipeline sheet, add FAIL sheet
1.4 | 2003-08-01 | update in Pipeline, Inventry sheet
1.5 | 2003-08-01 | update in Pipeline (wording, and formula in column I), HOLD (split SB and Module), FAIL, ASICstuffing sheets
1.6 | 2003-08-19 | update in Scurves (wording, >0.4fC), ASICstuffing, ASICyield(formula), add Location sheet, print area
1.7 | 2003-08-26 | update in Categories sheet (listing sums of GOOD+PASS for barrels)
1.8 | 2003-11-05 | correction of mistypo in categories definition, module for B3 and B4, temperature... <2 deg.C
1.9 | 2004-01-07 | add columns of STUCKCELL>2/link and BHN (block of high noise = partbonded in hybrid) at SDF=0.4, and modify counting of total , in ASICdefects sheet
2.0 | 2004-01-19 | add Quality and Sign-off columns in "Location" sheet. Sign-off "Category" is either of GOOD/PASS/FAIL.
2.1 | 2004-01-20 | add "Electrical special setting" in Quality columns in "Location" sheet
2.2 | 2004-02-05 | calculate "Modules classifed" in Pipeline from Categories
2.2.1 | 2004-02-23 | update Introduction sheet on description of HOLD sheet
2.3.1 | 2004-04-21 | update to include PASS2, SPARE, FAIL catogories defined in March 2004 SCT meeting and after
2.3.2 | 2004-04-26 | refined the MDM decay fitting function to account for the plateau current
2.3.3 | 2004-05-07 | update the hybrid metrology parameters for PASS etc. + revive HOLD columns for compatibility+ number of bug fixes
2.3.4 | 2004-05-14 | update PASS2/SPARE of hymxf(b), hymyf(b), and conp1y + add temp. diff. dT>4 deg.C for SPARE + bug fix + consistent s-curves >0.45 fC
2.4.1 | 2004-07-21 | after the June SCT week, creation of B6 PASS2 category (MD>300V, Vdd min<=3.8V), B6 (2<=dT<4), B5 (dT<2), and hymxf/hymyf/hymxb/hymyb<500um for PASS2
Barrel Module Categories
"SB" is the sensor-baseboard sandwich WITHOUT hybrid
"Module" is the final object, I.e., SB fitted WITH hybrid
When counted, SB's and Modules are exclusive each other.
Also, the entries in 1.1, 1.2, ..., are exclusive each other.
1 | GOOD
Fully completed and tested module, satisfying all specifications (mechanical and electrical).
For electrical performance, it is expected that the large majority of modules will have considerably less than the 1% bad channels of the specification.
Within Good are the subcategories:
1.1 | Good for any barrel
1.2 | Use only for barrel 5 or 6
1.25 | For barrel 6
(See separate proposal for these subcategories)
2 | PASS
The module just misses satisfying one or more of the mechanical specifications.
The purpose of the category is to keep modules in the tails of the expected mechanical distributions.
The number of Pass modules should therefore be much less than the number of Good modules.
A Pass module must still fully satisfy the electrical specification.
Pass modules are agreed to be usable in ATLAS, without further discussion.
Within Pass are the subcategories:
2.1 | Pass for any barrel
2.2 | Use only for barrel 5 or 6
2.25 | For barrel 6
The limits of quantities as measured for the Pass category: see the attached table
3 | HOLD
(This category is kept for historical reasons, and the entries are subtracted once the entries are classified in PASS2 or SPARE's.)
These are modules outside one or more of the Pass limits.
They are stopped in production at the point they are found to be outside the limit (ie a hybrid is not fitted if the baseboard-sensor sandwich is outside "pass" metrology values).
They are carefully stored for later assessment by the Barrel Module community.
3.1 | SB's
3.2 | Modules (I.e., SB with hybrid)
(e.g., I>4uA at 500V without Microdischarge(MD), MD<350V, Abnormally long current decay , lost channels>7/side, >15/total, etc)
3.3, 3.4 | PASS2
A wider (about 20% more than PASS) metrology cut parameters. The cut parameters are listed below
To be mated with hybrids with AA1 chips as much as possible
These are to be used in an EMERGENCY case in ATLAS
Within PASS2 are the subcategories:
3.3 | For any barrels
3.4 | For barrel 5 or 6
3.45 | For barrel 6
3.5, 3.6 | SPARE
Those that metrology is worse than PASS2, or if the electrical properties are out of spec. Fill the reasons in the SPARE sheet (see below)
These are to be used in an EXTREME EMERFGENCY case in ATLAS
To be mated with hybrids with AA1 chips as much as possible
Within SPARE are the subcategories:
3.5 | For any barrels
3.6 | For barrel 5 or 6
3.65 | For barrel 6
4 | FAIL
Modules that could never go in ATLAS,
for example broken or badly scratched detectors, gross mechanical errors (such as glue coming out), many bad channels due to bonding problems, broken ASICs that can't be replaced.
and out of SPARE limits
4.1 | SB's | (A FAIL S/B would not have a hybrid added to it)
4.2 | Modules (I.e., SB with hybrid)
5 | REWORK modules
Modules held back for rework that might make them usable,
e.g., replacing an ASIC, gluing on a replacement pitch adapter, re-bonding work.
6 | Classified
This "Classified" column is the sum of the above exclusive columns, in order to have the total number of classified SB and modules
First proposals for Modules to Select for Barrels 3 and 4
1 | Series (not pre-series) detectors.
2 | No sign of IV 'microdischarge' up to 500V bias (in nitrogen or dry air atmosphere)
3 | No history of unexplained bad IV behaviour (eg current very big on first test of module)
5 | No bad visual inspection features that could relate to HV robustness
(eg unusual amount of debris/marks near detector edges, messy detector-detector bonding that leaves any bonds flat near detector surface, broken bits of bond wire, etc.)
6 | Thermistor temperatures are as expected for test setup and difference in their temperature(dT) is dT<2 deg C
7 | Cooling facing b-angle within specification (I.e., <3 mrad)
8 | Any conclusions on irradiation hardness that might be established in future
Amendaments on 2004/06/28 (yyyy/mm/dd)
a1 | Thermistor temperatures difference dT< 2 degC for B3,B4,B5, and 2<=dT<4 deg.C for B6
a2 | Microdischarge (MD), MD>300V for B6, >350V for B5, and >500V for B3 and B4
a3 | Vdd for Bypass test, Vdd min = 3.5V for any barrel and Vdd min <=3.8V for B6
Barrel classification
|  |  | B3/B4 | B5/B6 | B6
1 | Pre-series sensors |  | No | Yes | <-
2 | MD>350V |  | >500V | >=350V | >=300V
3 | Bad current behaviour |  | No | Yes | <-
5 | Bad visual features |  | No | Yes | <-
6 | Thermistor T diff.>=2C |  | <2 degC | <- | 2<=dT<4 degC
7 | b angle >3 mrad |  | <=3 mrad | >3 mrad | <-
8 | Irradiation aspects
9 | Vdd min |  | 3.5V | <- | 3.5V< <=3.8V
Metrology parameters
(Measurement values are rounded down for classification)
|  | Parameter | GOOD | PASS | PASS2 | SPARE | FAIL
|  | mhx [um] | +/-30 | +/-40 | +/-50 | +/-60 | > +/-60
|  | mhy [um] | +/-30 | +/-40 | +/-50 | +/-60 | > +/-60
|  | msx [um] | +/-100 | +/-140 | +/-170 | +/-200 | > +/-200
|  | msy [um] | +/-30 | +/-40 | +/-50 | +/-60 | > +/-60
|  | sepf [um] | +/-10 | +/-20 | +/-30 | +/-40 | > +/-40
|  | sepb [um] | +/-10 | +/-20 | +/-30 | +/-40 | > +/-40
|  | midxf [um] | +/-10 | +/-20 | +/-30 | +/-40 | > +/-40
|  | midyf [um] | +/-5 | +/-8 | +/-10 | +/-15 | > +/-15 | exclusive of stereo
|  | a1 [mrad] | +/-0.13 | <- | +/-0.16 | +/-0.24 | > +/-0.24
|  | a2 [mrad] | +/-0.13 | <- | +/-0.16 | +/-0.24 | > +/-0.24
|  | a3 [mrad] | +/-0.13 | <- | +/-0.16 | +/-0.24 | > +/-0.24
|  | a4 [mrad] | +/-0.13 | <- | +/-0.16 | +/-0.24 | > +/-0.24
|  | stereo [mrad] | +/-0.13 | <- | +/-0.16 | +/-0.24 | > +/-0.24 | exclusive of midyf
|  | hymxf [um] | +/-100 | +/-200 | +/-500 | <- | >+/-500
|  | hymyf [um] | +/-100 | +/-200 | +/-500 | <- | >+/-500
|  | hymaf [mrad] | +/-3.145 | +/-3.145 | +/-6.290 | <- | >+/-6.290
|  | hymxb [um] | +/-100 | +/-200 | +/-500 | <- | >+/-500
|  | hymyb [um] | +/-100 | +/-200 | +/-500 | <- | >+/-500
|  | hymab [mrad] | +/-3.145 | +/-3.145 | +/-6.290 | <- | >+/-6.290
|  | conp1x [um] | +/-320 | +/-480 | +/-640 | <- | >+/-640
|  | conp1y [um] | +/-100 | +/-200 | +/-300 | <- | >+/-300
|  | maxZlower [mm] | -0.2 | <- | <- | <- | <-0.2 | absolute envelope
|  | maxZupper [mm] | 0.2 | <- | <- | <- | >0.2 | absolute envelope
|  | moduleThickness [mm] | 0.1 | <- | 0.15 | 0.2 | >0.2 | 1-sided
|  | optimalMaxZerrorLower [mm] | 0.05 | 0.07 | 0.09 | 0.11 | >0.11
|  | optimalMaxZerrorUpper [mm] | 0.05 | 0.07 | 0.09 | 0.11 | >0.11
|  | optimalRMSZerrorLower [mm] | 0.025 | <- | 0.03 | 0.03 | >0.03
|  | optimalRMSZerrorUpper [mm] | 0.025 | <- | 0.03 | 0.03 | >0.03
|  | loCoolingFacing a [mrad] | +/-0.5 | <- | +/-0.6 | +/-0.6 | >+/-0.6
|  | b [mrad] | +/-3 | +/-5 | +/-6 | +/-7 | >+/-7
|  | loCoolingFacingConcavity [mm] | +/-0.03 | <- | +/-0.04 | +/-0.05 | >+/-0.05
|  | capMaxThickness [mm] | 6.44 | <- | <- | <- | >6.44 | absolute envelope
|  | hyb1NearH [mm] | +/-0.19 | +/-0.25 | +/-0.35 | <- | >+/-0.35 | average= (hyb1LeftNearH+hyb1RightNearH)/2
|  | hyb1FarH[mm] | +/-0.19 | +/-0.25 | +/-0.35 | <- | >+/-0.35 | average= (hyb1LeftFarH+hyb1RightFarH)/2
|  | hyb2NearH [mm] | +/-0.19 | +/-0.25 | +/-0.35 | <- | >+/-0.35 | average= (hyb2LeftNearH+hyb2RightNearH)/2
|  | hyb2FarH [mm] | +/-0.19 | +/-0.25 | +/-0.35 | <- | >+/-0.35 | average= (hyb2LeftFarH+hyb2RightFarH)/2
|  | hyb1Concavity [mm] | +/-0.15 | +/-0.25 | +/-0.35 | <- | >+/-0.35
|  | hyb2Concavity [mm] | +/-0.15 | +/-0.25 | +/-0.35 | <- | >+/-0.35
|  | hyb1CapMaxH [mm] | 0.3 | <- | <- | <- | >0.3 | absolute envelope
|  | hyb2CapMaxH [mm] | 0.3 | <- | <- | <- | >0.3 | absolute envelope
|  | hybridMaxThickness [mm] | 0.44 | <- | <- | <- | >0.44 | absolute envelope
"exclusive": e.g., if midyf is in SPARE cut, the stereo must be below or equal to the next tightest cut, i.e., PASS2 cut
Electrical parameters
|  | Parameter | GOOD | <- | PASS2 | SPARE | FAIL
|  | I-V (No MD)[uA] | <=4@500V | <- | <- | <=4@350V | >4@350V
|  | Microdischarge onset voltage [V] | >=350 | <- | >=300 | >=150 | <150
|  | Microdischarge decay time (MDM) [hr] | <=1 | <- | <- | <=6 | >6
|  | Microdischarge decay plateau current [uA] | <=1 | <- | <- | <=4 | >4
|  | Number of lost channels (sideconsective, total) | <=7,<=15 | <- | <=10,<=20 | <=14,<=30 | >14, >30
|  | Bad S-curves >0.45fC | <=0.45fC | <- | <- | >0.45fC | ---
|  | Thermistor temp. diff. dT [deg.C] | <=4 | <- | <- | >4 | ---
|  | Vdd min. [V] | 3.5V | <- | 3.5V< <=3.8V | >3.8V | ---
Definition of MDM decay timeT: fit { I(t)=(I(0)-I(plateau))*exp(-t/T)+I(plateau) } to the decay part,
and approximately the time when { I(T)-I(plateau)}/{I(0)-I(plateau)}=1/2.7
Pipeline sheet:
1 | SB(Sensor-baseboard) started
2 | SB's sent/ready for classification
3 | SB's classified
4 | SB's sent/ready for hybrid mounting (="SB's classified" - ("SB's HOLD" + "SB's FAIL" in "Categories"))
5 | Modules sent/ready for wire-bonding (I.e., hybrid mounting completed = "SB's ready for hybrid mounting" - "Modules in progress at SB stage on date")
6 | Modules sent/ready for classification (I.e., wire-bonding completed)
7 | Modules classified (= "Classifed" - ("SB's HOLD"+"SB's FAIL") in "Categories")
- | Calculation/given | Modules in progress at SB stage on date(="SB's sent/ready for hybrid mounting" - "Modules sent/ready for wire-bonding")
- | Calculation/given | Modules in progress with hybrid mounted on date(="Modules sent/ready for wire-bonding" - "Modules classified")
Categories sheet:
1.1 | GOOD | for any barrel
1.2 |  | for B5/B6
1.25 |  | for B6
2.1 | PASS | for any barrel
2.2 |  | for B5/B6
2.25 |  | for B6
3.1 | (HOLD) | (SB's)
3.2 |  | (Modules)
3.3 | PASS2 | for any barrel
3.4 |  | for B5/B6
3.45 |  | B6
3.5 | SPARE | for any barrel |  | (If a module can not be assigned to one of "any barrel", "B5/B6", or "B6", it will go to 4.2 FAIL Modules)
3.6 |  | for B5/B6
3.65 |  | B6
4.1 | FAIL | SB's
4.2 |  | Modules
5 | REWORK | Modules
HOLD sheet: | Obsolete, but fill those SB and Modules if they are not yet classified into PASS2 or SPARE's
1 | SB out of PASS limits
2 | SB Others
3 | Module out of PASS limits
4 | I(500V)>4uA without microdischarge (MD<350) without annealing
5 | MD<350V
6 | Abnormally long current decay at 500V, >1hr
7 | Lost channels >7consective/side, >15/total
8 | Bad s-curves >0.45fC
9 | Others
for B5B6 sheet:
GOOD+PASS
1 | Pre-series sensors
2 | MD>=350V
3 | Bad current behaviour
5 | Bad visual features
6 | Thermistor T diff.>=2C
7 | b angle >3 mrad
8 | Irradiation aspects
PASS2+SPARE
11 | Pre-series sensors
12 | MD>=350V
13 | Bad current behaviour
15 | Bad visual features
16 | Thermistor T diff.>=2C
17 | b angle >3 mrad
18 | Irradiation aspects
for B6 sheet:
1 | MD>=300V
2 | Thermistor T diff >=2C
3 | 3.5V< Vdd min <= 3.8V
4 | Others
SPARE sheet:
1 | Metrology out of PASS2 (and inside of SPARE) limits
2 | I(350V)>4uA without microdischarge (MD<350) without annealing
3 | 150V<=MD<350V
4 | Abnormally long MD current decay , 1hr < decay time <= 6 hr, or high MD plateau current, 1uA< I_MD<=4 uA
5 | Lost channels, 10< consective/side<=14, 20< total <=30
6 | Bad s-curves >0.45fC
7 | Thermmistor temp diff dT>4 deg.C
8 | Bypass test Vdd min >3.8V
9 | Others
FAIL sheet:
1 | SB | Sensor damaged
2 | SB | BB damaged
3 | SB | Gross mechanical error (e.g. metrology out of SPARE limits, glue coming out)
4 | SB | Others
5 | Module | Sensor damaged
6 | Module | BB damaged
7 | Module | Gross mechanical error (e.g. metrology out of SPARE limits)
8 | Module | Abnormal leakge current (see Electrical Parameters limits)
9 | Module | Too many bad channels (see Electrical Parameters limits)
10 | Module | ASIC's non-replaceable
11 | Module | No assignable barrel
12 | Module | Others
REWORK sheet:
Modules are requiring further actions:
1 | replacing an ASIC
2 | replacing a pitch adaper
3 | rebonding wires
4 | replacing hybrid
5 | replacing connector
6 | further visual inspection
7 | cleaning
8 | others
Location sheet:
| Module id |  | First 7 digits can be automated with B3 cell
| Categories |  | 1.1~5 | Mandatory to be filled that automatically fills "Category" and "Barrel assignment" cells
Module location/usage
| Date |  | (dd/mm/yyyy) | Date of filling the row
| I-V |  | GOOD/PASS2/SPARE/FAIL
| I-V |  | Comment
| Electrical |  | GOOD/PASS2/SPARE/FAIL
| Electrical Special Setting |  | ISH=20, SDF=0.4
| Electrical |  | Comment
| S-curves Category |  | (ok(good) /negative /positive />0.45) |  |  | for good, "-": wiggle in negative threshold, "+": wiggles in both negative and positive threaholds, ">0.45": wiggles threshold > 0.45fC
| S-curves |  | Comment
| Category |  | GOOD/PASS/PASS2/SPARE/FAIL/REWORK, automatically filled from the "Categories" value
Reason for HOLD/FAIL
| Barrel assignment |  | Any/B5B6, automatically filled from the "Categories" value
Reason for B5B6
Sign-off comment

## Pipeline
Cluster | ND
Pipeline | ("sent" means either sent or ready to be sent)
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Cumulative
Date (yymmdd) | SB's started | SB's sent/ready for classification | SB's classified | SB's sent/ready for hybrid mounting | Modules sent/ready for wire-bonding | Modules sent/ready for classification | Modules classified | Modules in progress at SB stage on date (=(4)-(5)) | Modules in progress with hybrid mounted on date(=(5)-(7))
030501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
030601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
030701 | 31 | 31 | 31 | 28 | 28 | 28 | 28 | 0 | 0
030801 | 31 | 31 | 31 | 28 | 28 | 28 | 28 | 0 | 0
030901 | 31 | 31 | 31 | 28 | 28 | 28 | 28 | 0 | 0
031001 | 44 | 44 | 44 | 41 | 41 | 41 | 41 | 0 | 0
031101 | 55 | 55 | 55 | 52 | 52 | 52 | 52 | 0 | 0
031201 | 75 | 75 | 75 | 72 | 72 | 72 | 72 | 0 | 0
040101 | 87 | 87 | 87 | 84 | 84 | 84 | 84 | 0 | 0
040201 | 150 | 150 | 140 | 137 | 116 | 112 | 108 | 21 | 8
040301 | 182 | 181 | 164 | 159 | 134 | 133 | 133 | 25 | 1
040401 | 216 | 212 | 211 | 204 | 171 | 153 | 153 | 33 | 18
040501 | 246 | 244 | 242 | 235 | 189 | 182 | 177 | 46 | 12
040601 | 260 | 254 | 246 | 239 | 202 | 201 | 182 | 37 | 20
040701 | 272 | 266 | 266 | 266 | 211 | 201 | 182 | 55 | 29
040801 | 281 | 275 | 266 | 259 | 211 | 201 | 182 | 48 | 29
040901 | 289 | 289 | 284 | 277 | 220 | 212 | 206 | 57 | 14
041001 | 310 | 310 | 290 | 283 | 247 | 241 | 234 | 36 | 13
041101 | 318 | 318 | 290 | 283 | 266 | 260 | 251 | 17 | 15
041201 | 318 | 318 | 315 | 300 | 282 | 272 | 267 | 18 | 15
050101 | 318 | 318 | 315 | 300 | 282 | 272 | 267 | 18 | 15
050201 | 318 | 318 | 318 | 310 | 308 | 306 | 306 | 2 | 2

## Categories
Cluster | ND
Module categories (each column entry is exclusive each other)
| 1.1 | 1.2 | 1.25 | 2.1 | 2.2 | 2.25 | 3.1 | 3.2 | 3.3 | 3.4 | 3.45 | 3.5 | 3.6 | 3.65 | 4.1 | 4.2 | 5 | 6
Cumulative | GOOD |  |  | PASS |  |  | (HOLD) |  | PASS2 |  |  | SPARE |  |  | FAIL |  | REWORK |  | GOOD+PASS |  |  |  | YIELD
Date (yymmdd) | for any barrel | for B5/B6 | for B6 | for any barrel | for B5/B6 | forB6 | (SB's) | (Modules) | for any barrel | for B5/B6 | for B6 | for any barrel | for B5/B6 | for B6 | SB's | Modules | Modules | Classified | for any barrel | for B5/B6 | forB6 | total | PASS /(GOOD+PASS) | (GOOD+PASS) /Classified | (HOLD) /Classified | PASS2 /Classified | SPARE /Classified | FAIL /Classified | REWORK /Classified
030501 | [17 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
030601 | [17 empty] | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
030701 | 15 | 1 |  | 3 | 4 |  | 2 | 2 | [6 empty] | 1 | 3 |  | 31 | 18 | 5 | 0 | 23 | 30.43% | 74.19% | 12.9% | 0% | 0% | 12.9% | 0%
030801 | 15 | 1 |  | 3 | 4 |  | 2 | 2 | [6 empty] | 1 | 3 |  | 31 | 18 | 5 | 0 | 23 | 30.43% | 74.19% | 12.9% | 0% | 0% | 12.9% | 0%
030901 | 15 | 1 |  | 3 | 4 |  | 2 | 2 | [6 empty] | 1 | 3 |  | 31 | 18 | 5 | 0 | 23 | 30.43% | 74.19% | 12.9% | 0% | 0% | 12.9% | 0%
031001 | 20 | 6 |  | 4 | 4 |  | 2 | 4 | [6 empty] | 1 | 3 |  | 44 | 24 | 10 | 0 | 34 | 23.53% | 77.27% | 13.64% | 0% | 0% | 9.091% | 0%
031101 | 28 | 7 |  | 5 | 4 |  | 2 | 5 | [6 empty] | 1 | 3 |  | 55 | 33 | 11 | 0 | 44 | 20.45% | 80% | 12.73% | 0% | 0% | 7.273% | 0%
031201 | 41 | 10 |  | 7 | 4 |  | 2 | 7 | [6 empty] | 1 | 3 |  | 75 | 48 | 14 | 0 | 62 | 17.74% | 82.67% | 12% | 0% | 0% | 5.333% | 0%
040101 | 47 | 13 |  | 9 | 4 |  | 2 | 8 | [6 empty] | 1 | 3 |  | 87 | 56 | 17 | 0 | 73 | 17.81% | 83.91% | 11.49% | 0% | 0% | 4.598% | 0%
040201 | 63 | 16 |  | 11 | 4 |  | 2 | 11 | [6 empty] | 1 | 3 |  | 111 | 74 | 20 | 0 | 94 | 15.96% | 84.68% | 11.71% | 0% | 0% | 3.604% | 0%
040301 | 82 | 18 |  | 14 | 4 |  | 4 | 12 | [6 empty] | 1 | 4 |  | 139 | 96 | 22 | 0 | 118 | 15.25% | 84.89% | 11.51% | 0% | 0% | 3.597% | 0%
040401 | 92 | 24 |  | 14 | 4 |  | 6 | 17 | [6 empty] | 1 | 4 |  | 162 | 106 | 28 | 0 | 134 | 13.43% | 82.72% | 14.2% | 0% | 0% | 3.086% | 0%
040501 | 100 | 27 |  | 16 | 5 |  | 6 | 10 | 3 | 0 |  |  | 7 |  | 1 | 9 |  | 184 | 116 | 32 | 0 | 148 | 14.19% | 80.43% | 8.696% | 1.63% | 3.804% | 5.435% | 0%
040601 | 105 | 27 |  | 16 | 5 |  | 6 | 10 | 3 | 0 |  |  | 7 |  | 1 | 9 |  | 189 | 121 | 32 | 0 | 153 | 13.73% | 80.95% | 8.466% | 1.587% | 3.704% | 5.291% | 0%
040701 | 105 | 27 |  | 16 | 5 |  | 6 | 10 | 3 | 0 |  |  | 7 |  | 1 | 9 |  | 189 | 121 | 32 | 0 | 153 | 13.73% | 80.95% | 8.466% | 1.587% | 3.704% | 5.291% | 0%
040801 | 105 | 27 |  | 17 | 5 |  | 6 | 0 | 2 | 0 | 2 | 2 | 7 | 0 | 1 | 15 |  | 189 | 122 | 32 | 0 | 154 | 14.29% | 81.48% | 3.175% | 2.116% | 4.762% | 8.466% | 0%
040901 | 110 | 30 |  | 17 | 5 |  | 6 | 0 | 2 | 0 | 2 | 4 | 8 | 0 | 1 | 15 | 13 | 213 | 127 | 35 | 0 | 162 | 13.58% | 76.06% | 2.817% | 1.878% | 5.634% | 7.512% | 6.103%
041001 | 126 | 32 |  | 22 | 5 |  | 6 | 0 | 3 | 0 | 2 | 4 | 10 | 0 | 1 | 15 | 15 | 241 | 148 | 37 | 0 | 185 | 14.59% | 76.76% | 2.49% | 2.075% | 5.809% | 6.639% | 6.224%
041101 | 146 | 38 |  | 22 | 6 |  | 6 | 0 | 2 | 0 | 2 | 4 | 9 | 0 | 1 | 16 | 6 | 258 | 168 | 44 | 0 | 212 | 13.21% | 82.17% | 2.326% | 1.55% | 5.039% | 6.589% | 2.326%
041201 | 155 | 41 |  | 23 | 5 |  | 6 | 0 | 4 | 0 | 2 | 5 | 8 | 2 | 1 | 18 | 4 | 274 | 178 | 46 | 0 | 224 | 12.5% | 81.75% | 2.19% | 2.19% | 5.474% | 6.934% | 1.46%
050101 | 155 | 41 |  | 23 | 5 |  | 6 | 0 | 4 | 0 | 2 | 5 | 8 | 2 | 1 | 18 | 4 | 274 | 178 | 46 | 0 | 224 | 12.5% | 81.75% | 2.19% | 2.19% | 5.474% | 6.934% | 1.46%
050201 | 170 | 49 |  | 22 | 5 | 2 | 6 | 0 | 7 | 1 | 1 | 5 | 7 | 6 | 1 | 27 | 4 | 313 | 192 | 54 | 2 | 248 | 11.69% | 79.23% | 1.917% | 2.875% | 5.751% | 8.946% | 1.278%

## forB5B6
Cluster | ND
Modules for B5/B6
Reasons:
| GOOD+PASS | [6 empty] | PASS2+SPARE
Cumulative | 1 | 2 | 3 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 15 | 16 | 17 | 18
Date (yymmdd) | Pre-series sensors | MD>=350V | Bad current behaviour | Bad visual features | Thermistor T diff.>=2C | b angle >3 mrad | Irradiation aspects | Pre-series sensors | MD>=350V | Bad current behaviour | Bad visual features | Thermistor T diff.>=2C | b angle >3 mrad | Irradiation aspects
030501
030601
030701 |  | 2 |  |  |  | 3
030801 |  | 2 |  |  |  | 3
030901 |  | 2 |  |  |  | 3
031001 |  | 6 |  |  |  | 3
031101 |  | 9 |  |  |  | 3
031201 |  | 12 |  |  |  | 3
040101 |  | 15 |  |  |  | 3
040201 |  | 18 |  |  |  | 3
040301 |  | 19 |  |  |  | 3
040401 |  | 25 |  |  |  | 3
040501 |  | 31 |  |  |  | 1 |  |  |  | 7
040601 |  | 31 |  |  |  | 1 |  |  |  | 7
040701 |  | 31 |  |  |  | 1 |  |  |  | 7
040801 |  | 31 |  |  |  | 1 |  |  |  | 7
040901 |  | 34 |  |  |  | 1 |  |  |  | 7
041001 |  | 37 |  |  |  | 1 |  |  |  | 7
041101 |  | 45 |  |  |  | 1 |  |  |  | 7
041201 |  | 45 | 1 |  |  | 1 |  |  |  | 8
050101 |  | 45 | 1 |  |  | 1 |  |  |  | 8
050201 |  | 52 | 1 |  |  | 1 |  |  |  | 9

## forB6
Cluster | ND
Modules for B6
Reasons:
Cumulative | 1 | 2 | 3 | 4
Date (yymmdd) | MD>=300V | Thermistor T diff.>=2C | Vdd min 3.5V< <=3.8V | Others
030501
030601
030701
030801
030901
031001
031101
031201
040101
040201
040301
040401
040501
040601
040701
040801 | 2
040901 | 2
041001 | 2
041101 | 2
041201 | 3
050101 | 3
050201 | 8

## HOLD
Cluster | ND
SB or Modules in HOLD (This sheet is kept for historical reason)
Reasons:
| SB |  | Module
Cumulative | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Date (yymmdd) | Out of PASS limits | Others | Out of PASS limit | I(500V)>4uA W/O MD<350V | MD<350V | Abnormally long current decay, >1hr | Lost ch. >7consective/side, >15/total | Bad s-curves >0.45fC | Others
030501
030601
030701 |  | 2 |  | 1 |  |  |  |  | 2
030801 |  | 2 |  | 1 |  |  |  |  | 2
030901 |  | 2 |  | 1 |  |  |  |  | 2
031001 |  | 2 |  | 1 | 1 |  |  |  | 2
031101 |  | 2 | 1 | 1 | 1 |  |  |  | 2
031201 |  | 2 | 1 | 3 | 1 |  |  |  | 2
040101 |  | 2 | 1 | 4 | 1 |  |  |  | 2
040201 |  | 2 | 1 | 5 | 1 |  | 1 |  | 2
040301 |  | 4 | 2 | 6 | 1 |  | 1 |  | 2
040401 | 1 | 5 | 2 | 8 | 3 |  | 1 |  | 3
040501 |  |  | 1 | 7 | 3 |  |  |  | 2
040601 |  |  | 1 | 7 | 3 |  |  |  | 2
040701 |  |  | 1 | 7 | 3 |  |  |  | 2
040801
040901
041001
041101
041201
050101
050201

## SPARE
Cluster | ND
SB or Modules in SPARE
Reasons:
Module
Cumulative | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Date (yymmdd) | Metrology out of PASS2 (and inside of SPARE) limits | I(350V)>4uA without micro discharge (MD<350) without annealing | 150V<=MD<350V | Long MD current decay , 1hr < decay time <= 6 hr | Lost channels, 10< consective /side<=14, 20< total <=30 | Bad s-curves >0.45fC | Thermistor temp diff dT>4 deg.C | Bypass test Vdd min >3.8V | Others
030501
030601
030701
030801
030901
031001
031101
031201
040101
040201
040301
040401
040501 |  | 1 | 6
040601 |  | 1 | 6
040701 |  | 1 | 6
040801 | 1 | 2 | 4 | [5 empty] | 2
040901 | 1 | 2 | 4 |  | 3
041001 | 1 | 2 | 4 |  | 3 |  |  |  | 2
041101 | 1 | 2 | 4 |  | 2 |  |  |  | 2
041201 | 1 | 4 | 4 |  | 4 |  |  |  | 2
050101
050201 | 1 | 6 | 6 |  | 3 |  |  |  | 2

## FAIL
Cluster | ND
SB or Modules in FAIL
Reasons:
| SB |  |  |  | Module
Cumulative | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Date (yymmdd) | Sensor damaged | BB damaged | Gross mechanical error (e.g. metrology out of SPARE limits, glue coming out) | Others | Sensor damaged | BB damaged | Gross mechanical error (e.g. metrology out of SPARE limits) | Abnormal leakge current (see Electrical Parameters limits) | Too many bad channels (see Electrical Parameters limits) | ASIC's non-replaceable | No assignable barrel | Others
030501
030601
030701 |  |  |  | 1 |  |  | 1 | 2
030801 |  |  |  | 1 |  |  | 1 | 2
030901 |  |  |  | 1 |  |  | 1 | 2
031001 |  |  |  | 1 |  |  | 1 | 2
031101 |  |  |  | 1 |  |  | 1 | 2
031201 |  |  |  | 1 |  |  | 1 | 2
040101 |  |  |  | 1 |  |  | 1 | 2
040201 |  |  |  | 1 |  |  | 1 | 2
040301 |  |  |  | 1 |  |  | 1 | 3
040401 |  |  |  | 1 |  |  | 1 | 3
040501 |  |  |  | 1 |  |  | 3 | 5 | 1
040601 |  |  |  | 1 |  |  | 3 | 5 | 1
040701 |  |  |  | 1 |  |  | 3 | 5 | 1
040801 |  |  |  | 1 |  |  | 3 | 5 | 1
040901 |  |  |  | 1 |  |  | 3 | 5 | 1
041001 |  |  |  | 1 |  |  | 3 | 11 | 2
041101 |  |  |  | 1 |  |  | 4 | 12 | 2
041201 |  |  |  | 2
050101 |  |  |  | 2
050201 |  |  |  | 2 |  |  | 4 | 17 | 1 | 3

## REWORK
Cluster | ND
Modules in REWORK
Reasons: requiring ...
Cumulative | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Date (yymmdd) | replacing ASIC | replacing PA | rebonding wires | replacing hybrid | replacing connector | further visual inspection | cleaning | others
030501
030601
030701
030801
030901
031001
031101
031201
040101
040201
040301
040401
040501
040601
040701
040801
040901 | 13
041001 | 13
041101 | 6
041201 | 1 | [6 empty] | 4
050101 | 0 | [6 empty] | 4
050201 | 0 | [6 empty] | 4

## Scurves
Cluster | ND
S-curve wiggles in Noise-Occupancy plots in modules (GOOD+PASS)
Cumulative | 1 | 2 | 3
| Wiggles |  |  | Fraction
Date (yymmdd) | in negative(-) threshold | in both +,-thresholds | containing >0.45 fC | in negative(-) or both (+,-) threshold | in both +,-thresholds | containing >0.45 fC
030501 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
030601 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
030701 | 9 | 10 |  | 82.61% | 43.48% | 0%
030801 | 9 | 10 |  | 82.61% | 43.48% | 0%
030901 | 9 | 10 |  | 82.61% | 43.48% | 0%
031001 | 14 | 14 |  | 82.35% | 41.18% | 0%
031101 | 16 | 24 |  | 90.91% | 54.55% | 0%
031201 | 23 | 25 |  | 77.42% | 40.32% | 0%
040101 | 26 | 28 |  | 73.97% | 38.36% | 0%
040201 | 35 | 36 |  | 75.53% | 38.3% | 0%
040301 | 43 | 43 |  | 72.88% | 36.44% | 0%
040401 | 47 | 48 |  | 70.9% | 35.82% | 0%
040501 | 56 | 47 |  | 69.59% | 31.76% | 0%
040601 | 58 | 47 |  | 68.63% | 30.72% | 0%
040701 | 58 | 47 |  | 68.63% | 30.72% | 0%
040801 | 58 | 47 |  | 68.18% | 30.52% | 0%
040901 | 61 | 47 |  | 66.67% | 29.01% | 0%
041001 | 69 | 53 |  | 65.95% | 28.65% | 0%
041101 | 71 | 54 |  | 58.96% | 25.47% | 0%
041201 | 72 | 55 |  | 56.7% | 24.55% | 0%
050101 | 72 | 55 |  | 56.7% | 24.55% | 0%
050201 | 73 | 52 |  | 50.81% | 21.14% | 0%

## ASICstuffing
Cluster | ND
ASIC stuffing (hybrid counts)
| 1 | 2 | 3 | 4 | 5.1 | 5.2
Cumulative | GOOD | REPAIRED | HOLD | FAIL | STARTED |  | YIELD
Date (yymmdd) | ready for hybrid mounting | e.g GOOD after ASIC replacement | e.g., with defective ASIC's | damaged, no recovery | ASIC stuffing | ASIC-hybrids Classified | (GOOD+REPAIRED)/SUM(1to4) | anticipated
030501 | 5.2: 0 | #DIV/0! | #DIV/0!
030601 | 5.2: 0 | #DIV/0! | #DIV/0!
030701 | 5.2: 0 | #DIV/0! | #DIV/0!
030801 | 5.2: 0 | #DIV/0! | #DIV/0!
030901 | 5.2: 0 | #DIV/0! | #DIV/0!
031001 | 5.2: 0 | #DIV/0! | #DIV/0!
031101 | 5.2: 0 | #DIV/0! | #DIV/0!
031201 | 5.2: 0 | #DIV/0! | #DIV/0!
040101 | 5.2: 0 | #DIV/0! | #DIV/0!
040201 | 5.2: 0 | #DIV/0! | #DIV/0!
040301 | 5.2: 0 | #DIV/0! | #DIV/0!
040401 | 5.2: 0 | #DIV/0! | #DIV/0!
040501 | 5.2: 0 | #DIV/0! | #DIV/0!
040601 | 5.2: 0 | #DIV/0! | #DIV/0!
040701 | 5.2: 0 | #DIV/0! | #DIV/0!
040801 | 5.2: 0 | #DIV/0! | #DIV/0!
040901 | 5.2: 0 | #DIV/0! | #DIV/0!
041001 | 5.2: 0 | #DIV/0! | #DIV/0!
041101 | 5.2: 0 | #DIV/0! | #DIV/0!
041201 | 5.2: 0 | #DIV/0! | #DIV/0!
050101 | 5.2: 0 | #DIV/0! | #DIV/0!
050201 | 5.2: 0 | #DIV/0! | #DIV/0!

## ASICdefects
Cluster | ND
ASIC defect classification (ASIC counts)
Cumulative
Large Gain Spread (LGS)
Date (yymmdd) | Dead | STUCK-CELL | STUCK-CELL >2/link | ISH=30uA Warm | ISH=30uA COLD | ISH=20uA COLD | TrimDAC loading failed | Negative offset | High offset | Low gain (<45 mV/fC) | Abnormal cal line | SAWTOOTH s-curve | BLG=BHN=BPB (SDF=default) | BLG=BHN=BPB (SDF=0.4) | Others | defective ASIC's
030501 | [15 empty] | 0
030601 | [15 empty] | 0
030701 | [15 empty] | 0
030801 | [15 empty] | 0
030901 | [15 empty] | 0
031001 | [15 empty] | 0
031101 | [15 empty] | 0
031201 | [15 empty] | 0
040101 | [15 empty] | 0
040201 | [15 empty] | 0
040301 | [15 empty] | 0
040401 | [15 empty] | 0
040501 | [15 empty] | 0
040601 | [15 empty] | 0
040701 | [15 empty] | 0
040801 | [15 empty] | 0
040901 | [15 empty] | 0
041001 | [15 empty] | 0
041101 | [15 empty] | 0
041201 | [15 empty] | 0
050101
050201
Note:
| BLG | Block of Low Gain
| BHN | Block of High Noise
| BPB | Block of "part-bonded" (in hybrids)

## ASICyield
Cluster | ND
ASIC loss yield
Cumulative
Date (yymmdd) | defective ASIC's | lost in FAILed hybrids | Visual rejects | lost in handling | lost | Loss Yield
030501 | 0 | 0 |  |  | 0 | #DIV/0!
030601 | 0 | 0 |  |  | 0 | #DIV/0!
030701 | 0 | 0 |  |  | 0 | #DIV/0!
030801 | 0 | 0 |  |  | 0 | #DIV/0!
030901 | 0 | 0 |  |  | 0 | #DIV/0!
031001 | 0 | 0 |  |  | 0 | #DIV/0!
031101 | 0 | 0 |  |  | 0 | #DIV/0!
031201 | 0 | 0 |  |  | 0 | #DIV/0!
040101 | 0 | 0 |  |  | 0 | #DIV/0!
040201 | 0 | 0 |  |  | 0 | #DIV/0!
040301 | 0 | 0 |  |  | 0 | #DIV/0!
040401 | 0 | 0 |  |  | 0 | #DIV/0!
040501 | 0 | 0 |  |  | 0 | #DIV/0!
040601 | 0 | 0 |  |  | 0 | #DIV/0!
040701 | 0 | 0 |  |  | 0 | #DIV/0!
040801 | 0 | 0 |  |  | 0 | #DIV/0!
040901 | 0 | 0 |  |  | 0 | #DIV/0!
041001 | 0 | 0 |  |  | 0 | #DIV/0!
041101 | 0 | 0 |  |  | 0 | #DIV/0!
041201 | 0 | 0 |  |  | 0 | #DIV/0!
050101
050201

## Inventory
Cluster | ND
Inventory
Cumulative | Received: |  |  |  |  | Used (=started (upto FAIL's)): |  |  |  |  | Lost, damaged, in handling and assembly (not counted as started) |  |  |  |  | Stock:
Date (yymmdd) | Sensors | Base-boards | ASIC's | PC-hybrids | ASIC-hybrids | Sensors | Base-boards | ASIC's | PC-hybrids | ASIC-hybrids | Sensors | Base-boards | ASIC's | PC-hybrids | ASIC-hybrids | Sensors | Base-boards | ASIC's | PC-hybrids | ASIC-hybrids
030501 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
030601 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
030701 | 1914 | 178 |  |  |  | 124 | 31 | 0 | 0 |  | 16 |  |  |  |  | 1774 | 147 | 0 | 0 | 0
030801 | 1914 | 178 |  |  |  | 124 | 31 | 0 | 0 |  | 16 |  |  |  |  | 1774 | 147 | 0 | 0 | 0
030901 | 1914 | 178 |  |  |  | 124 | 31 | 0 | 0 |  | 16 |  |  |  |  | 1774 | 147 | 0 | 0 | 0
031001 | 1914 | 178 |  |  | 69 | 176 | 44 | 0 | 0 |  | 18 |  |  |  |  | 1720 | 134 | 0 | 0 | 69
031101 | 1914 | 178 |  |  | 83 | 220 | 55 | 0 | 0 |  | 18 |  |  |  |  | 1676 | 123 | 0 | 0 | 83
031201 | 1914 | 178 |  |  | 95 | 300 | 75 | 0 | 0 |  | 18 |  |  |  |  | 1596 | 103 | 0 | 0 | 95
040101 | 1914 | 178 |  |  | 122 | 348 | 87 | 0 | 0 |  | 18 |  |  |  |  | 1548 | 91 | 0 | 0 | 122
040201 | 1914 | 300 |  |  | 151 | 600 | 150 | 0 | 0 |  | 18 |  |  |  |  | 1296 | 150 | 0 | 0 | 151
040301 | 1814 | 300 |  |  | 154 | 728 | 182 | 0 | 0 |  | 18 |  |  |  |  | 1068 | 118 | 0 | 0 | 154
040401 | 1298 | 300 |  |  | 181 | 864 | 216 | 0 | 0 |  | 18 |  |  |  |  | 416 | 84 | 0 | 0 | 181
040501 | 1298 | 320 |  |  | 200 | 984 | 246 | 0 | 0 |  | 18 |  |  |  |  | 296 | 74 | 0 | 0 | 200
040601 | 1298 | 320 |  |  | 222 | 1040 | 260 | 0 | 0 |  | 18 |  |  |  |  | 240 | 60 | 0 | 0 | 222
040701 | 1298 | 320 |  |  | 234 | 1088 | 272 | 0 | 0 |  | 18 |  |  |  |  | 192 | 48 | 0 | 0 | 234
040801 | 1298 | 320 |  |  | 234 | 1124 | 281 | 0 | 0 |  | 18 |  |  |  |  | 156 | 39 | 0 | 0 | 234
040901 | 1298 | 320 |  |  | 263 | 1156 | 289 | 0 | 0 |  | 18 |  |  |  |  | 124 | 31 | 0 | 0 | 263
041001 | 1298 | 320 |  |  | 316 | 1240 | 310 | 0 | 0 |  | 18 |  |  |  |  | 40 | 10 | 0 | 0 | 316
041101 | 1298 | 320 |  |  | 316 | 1272 | 318 | 0 | 0 |  | 18 |  |  |  |  | 8 | 2 | 0 | 0 | 316
041201 | 1298 | 320 |  |  | 316 | 1272 | 318 | 0 | 0 |  | 18 |  |  |  |  | 8 | 2 | 0 | 0 | 316
050101 | 1298 | 320 |  |  | 316 | 1272 | 318 | 0 | 0 |  | 18 |  |  |  |  | 8 | 2 | 0 | 0 | 316
050201 | 1298 | 320 |  |  | 316 | 1272 | 318 | 0 | 0 | 308 | 18 |  |  |  | 2 | 8 | 2 | 0 | 0 | 6

## Location
Cluster | ND
Module location | outside of assembly location, e.g., irradiation, beamtest, macro assembly site
Module inst. id | 2022017 | 2022017(Japan), 2022038(Nordic), 2022004(US), 2022033(UK) |  | Quality | [6 empty] | Sign-off
Module id | Categories (1.1~5) | Module location/usage | Date (dd/mm/yyyy) | I-V GOOD /PASS2 /SPARE /FAIL | I-V Comment | Electrical GOOD /PASS2 /SPARE /FAIL | Electrical Special Setting (ISH=20,SDF=0.4) | Electrical Comment | S-curves Category ((ok or good) /negative /positive />0.45) | S-curves Comment | Category GOOD /PASS /PASS2 /SPARE /FAIL | Reason for FAIL | Barrel assignment Any/B5B6/B6 | Reason for B5B6 or B6 | Sign-off Comment
20220380200006 | 3.6 | irradiated | [6 empty] | positive |  | SPARE |  | B5/B6
20220380200007 | 2.1 | [7 empty] | OK |  | PASS |  | ANY
20220380200008 | 2.1 | [7 empty] | OK |  | PASS |  | ANY
20220380200009 | 2.1 | [7 empty] | positive |  | PASS |  | ANY
20220380200010 | 2.1 | [7 empty] | negative |  | PASS |  | ANY
20220380200011 | 4.2 | [7 empty] | OK |  | FAIL
20220380200012 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380200013 | 4.2 | [7 empty] | OK |  | FAIL
20220380200014 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380200015 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200016 | 2.1 | [7 empty] | positive |  | PASS |  | ANY
20220380200017 | 3.5 | [7 empty] | OK |  | SPARE |  | ANY
20220380200018 | 2.2 | [7 empty] | OK |  | PASS |  | B5/B6
20220380200019 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200020 | 3.3 | [7 empty] | OK |  | PASS2 |  | ANY
20220380200021 | 4.2 | [7 empty] | positive |  | FAIL
20220380200022 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200023 | 2.1 | [7 empty] | negative |  | PASS |  | ANY
20220380200024 | 2.1 | [7 empty] | negative |  | PASS |  | ANY
20220380200025 | 2.1 | [7 empty] | negative |  | PASS |  | ANY
20220380200026 | 2.2 | [7 empty] | OK |  | PASS |  | B5/B6
20220380200030 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200031 | 3.6 | [7 empty] | negative |  | SPARE |  | B5/B6
20220380200032 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200033 | 4.2 | [7 empty] | OK |  | FAIL
20220380200034 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380200035 | 2.2 | [7 empty] | negative |  | PASS |  | B5/B6
20220380200036 | 2.25 | [7 empty] | positive |  | PASS |  | B6
20220380200037 | 1.2 | [7 empty] | positive |  | GOOD |  | B5/B6
20220380200038 | 3.6 | [7 empty] | OK |  | SPARE |  | B5/B6
20220380200039 | 2.1 | [7 empty] | OK |  | PASS |  | ANY
20220380200040 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200042 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200043 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380200045 | 3.65 | [7 empty] | positive |  | SPARE |  | B6
20220380200046 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380200047 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380200048 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380200049 | 1.2 | [7 empty] | positive |  | GOOD |  | B5/B6
20220380200050 | 1.2 | [7 empty] | positive |  | GOOD |  | B5/B6
20220380200051 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380200052 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380200053 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200054 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200055 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380200056 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200057 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200058 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200059 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200060 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380200061 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200066 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200067 | 2.1 | [7 empty] | negative |  | PASS |  | ANY
20220380200068 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380200069 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380200070 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380200071 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380200072 | 4.2 | [9 empty] | FAIL
20220380200073 | 2.1 | [7 empty] | OK |  | PASS |  | ANY
20220380200074 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380200075 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380200076 | 4.2 | [7 empty] | negative |  | FAIL
20220380200077 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380200078 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380200079 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380200080 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380200081 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380200082 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380200083 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380200084 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380200085 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380200086 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380200087 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380200088 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380200089 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380200090 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380200091 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380200092 | 4.2 | [7 empty] | negative |  | FAIL
20220380200093 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380200094 | 1.2 | [7 empty] | positive |  | GOOD |  | B5/B6
20220380200095 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220330200050 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220330200100 | 4.2 | [9 empty] | FAIL
20220330200116 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220330200117 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220330200118 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220330200119 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220330200120 | 1.2 | [7 empty] | positive |  | GOOD |  | B5/B6
20220330200122 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220330200123 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220330200124 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220330200125 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220330200126 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220330200127 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220330200128 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220330200129 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220330200130 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220330200136 | 1.2 | [7 empty] | positive |  | GOOD |  | B5/B6
20220330200137 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220330200138 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220330200139 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000096 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000097 | 4.2 | [7 empty] | OK |  | FAIL
20220380000098 | 4.2 | [7 empty] | OK |  | FAIL
20220380000099 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000100 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000101 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380000102 | 3.3 | [7 empty] | negative |  | PASS2 |  | ANY
20220380000103 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380000104 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000105 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000106 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000107 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000108 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000109 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000110 | 1.2 | [7 empty] | positive |  | GOOD |  | B5/B6
20220380000111 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000112 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000113 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000114 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000115 | 4.2 | [9 empty] | FAIL
20220380000116 | 2.1 | [7 empty] | negative |  | PASS |  | ANY
20220380000117 | 2.1 | [7 empty] | positive |  | PASS |  | ANY
20220380000118 | 2.2 | [7 empty] | positive |  | PASS |  | B5/B6
20220380000119 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000120 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000121 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380000122 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000123 | 2.1 | [7 empty] | negative |  | PASS |  | ANY
20220380000124 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380000125 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380000126 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000127 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000128 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380000129 | 3.6 | [7 empty] | OK |  | SPARE |  | B5/B6
20220380000131 | 4.2 | [9 empty] | FAIL
20220380000132 | 2.1 | [7 empty] | OK |  | PASS |  | ANY
20220380000133 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380000135 | 2.25 | [7 empty] | OK |  | PASS |  | B6
20220380000136 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000137 | 4.2 | [9 empty] | FAIL
20220380000138 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000139 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000140 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000141 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380000142 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000143 | 2.25 | [7 empty] | OK |  | PASS |  | B6
20220380000144 | 3.5 | [7 empty] | OK |  | SPARE |  | ANY
20220380000145 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000146 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380000147 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000148 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000149 | 1.2 | [7 empty] | positive |  | GOOD |  | B5/B6
20220380000150 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380000151 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380000152 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000153 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000154 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000155 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380000156 | 4.2 | [6 empty] | AA1 | OK |  | FAIL
20220380000157 | 4.2 | [6 empty] | AA1 |  |  | FAIL
20220380000158 | 3.6 | [6 empty] | AA1 | positive |  | SPARE |  | B5/B6
20220380000159 | 3.3 | [6 empty] | AA1 | negative |  | PASS2 |  | ANY
20220380000160 | 3.5 | [6 empty] | AA1 | OK |  | SPARE |  | ANY
20220380000161 | [7 empty] | AA1 |  |  | REWORK
20220380000162 | 3.6 | [6 empty] | AA1 | OK |  | SPARE |  | B5/B6
20220380000163 | 2.1 | [6 empty] | AA1 | negative |  | PASS |  | ANY
20220380000164 | 3.6 | [6 empty] | AA1 | negative |  | SPARE |  | B5/B6
20220380000165 | 1.1 | [6 empty] | AA1 | positive |  | GOOD |  | ANY
20220380000166 | 2.1 | [7 empty] | negative |  | PASS |  | ANY
20220380000167 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000168 | 1.1 | chip replaced | [6 empty] | positive |  | GOOD |  | ANY
20220380000169 | 4.2 | chip replaced | [8 empty] | FAIL
20220380000170 | 1.1 | chip replaced | [6 empty] | OK |  | GOOD |  | ANY
20220380000171 | 1.2 | [7 empty] | negative |  | GOOD |  | B5/B6
20220380000172 | [14 empty] | Hybrid hold
20220380000173 | 3.6 | [7 empty] | positive |  | SPARE |  | B5/B6
20220380000174 | 4.2 | [9 empty] | FAIL
20220380000175 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000176 | 4.2 | chip replaced | [8 empty] | FAIL
20220380000177 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380000178 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000179 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000180 | 2.1 | [7 empty] | OK |  | PASS |  | ANY
20220380000181 | 1.1 | chip replaced | [6 empty] | OK |  | GOOD |  | ANY
20220380000182 | 2.1 | [7 empty] | OK |  | PASS |  | ANY
20220380000183 | 1.1 | BLG problem | [6 empty] | OK |  | GOOD |  | ANY
20220380000184 | 1.1 | [6 empty] | AA1 | positive |  | GOOD |  | ANY
20220380000185 | 3.4 | chip replaced | [5 empty] | AA1 | positive |  | PASS2 |  | B5/B6
20220380000186 | 3.5 | spare, b3 | [5 empty] | AA1 | OK |  | SPARE |  | ANY
20220380000187 | 1.2 | chip replaced | [6 empty] | OK |  | GOOD |  | B5/B6
20220380000188 | 1.1 | chip replaced | [6 empty] | negative |  | GOOD |  | ANY
20220380000189 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000190 | 4.2 | chip replacement failed | [6 empty] | OK |  | FAIL
20220380000191 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000192 | 4.2 | chip replacement failed | [8 empty] | FAIL
20220380000193 | 4.2 | chip replacement failed | [8 empty] | FAIL
20220380000194 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380000195 | 2.2 | [7 empty] | negative |  | PASS |  | B5/B6
20220380000196 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000197 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000198 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000199 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000200 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000201 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000202 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000203 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000204 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000205 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000206 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000207 | 4.2 | [9 empty] | FAIL
20220380000208 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000209 | 4.2 | High noise | [8 empty] | FAIL
20220380000210 | 1.1 | chip replaced | [6 empty] | OK |  | GOOD |  | ANY
20220380000211 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000212 | 4.2 | [9 empty] | FAIL
20220380000213
20220380000214
20220380000215 | 4.2 | [9 empty] | FAIL
20220380000216 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000217 | 1.1 | [6 empty] | AA1 | positive |  | GOOD |  | ANY
20220380000218 | 5 | rework
20220380000219 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000220 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000221 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000222 | 1.1 | chip replaced | [6 empty] | negative |  | GOOD |  | ANY
20220380000223 | 1.1 | chip replaced | [6 empty] | OK |  | GOOD |  | ANY
20220380000224 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000225 | 2.1 | [7 empty] | OK |  | PASS |  | ANY
20220380000226 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000227 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380000228 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380000229 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000230 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000231 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000232 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000233 | 1.1 | [9 empty] | GOOD |  | ANY
20220380000234 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000235 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000236 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000237 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000238 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000239 |  | hybrid hold
20220380000240 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000241
20220380000242 | [7 empty] | AA1
20220380000243 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000244 | 1.1 | [7 empty] | positive |  | GOOD |  | ANY
20220380000245 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000246 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000247 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000248 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380000249 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000250 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000251 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000252 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000254 | 5 | rework
20220380000255 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000256 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000257 | 3.5 | [6 empty] | AA1 | OK |  | SPARE |  | ANY
20220380000258 | 4.2 | [6 empty] | AA1 |  |  | FAIL
20220380000259 | 4.2 | [9 empty] | FAIL
20220380000260 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000261 | 1.1 | [6 empty] | AA1 |  |  | GOOD |  | ANY
20220380000262 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000263 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000264 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000265 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000266 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000267 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000268 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000269 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000270 | 1.2 | [7 empty] | OK |  | GOOD |  | B5/B6
20220380000271 | 3.3 | [7 empty] | OK |  | PASS2 |  | ANY
20220380000272 | 4.2 |  |  |  |  | GOOD |  | AA1 | OK |  | FAIL | cooling facing
20220380000273 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000274 | 1.1 | [6 empty] | AA1 |  |  | GOOD |  | ANY
20220380000275 | 2.2 | stuckcell | [5 empty] | AA1 | OK |  | PASS |  | B5/B6
20220380000276 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000277 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000278 | 1.1 | [6 empty] | AA1 | negative |  | GOOD |  | ANY
20220380000279 | 5 | rework | [5 empty] | AA1 | OK
20220380000280 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000281 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000282 | 1.2 | preliminary metrology | [5 empty] | AA1 | OK |  | GOOD |  | B5/B6
20220380000283 | 1.1 | [7 empty] | OK |  | GOOD |  | ANY
20220380000284 | 1.2 | preliminary metrology | [5 empty] | AA1 | negative |  | GOOD |  | B5/B6
20220380000285 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000286 | 1.1 | [6 empty] | AA1 | negative |  | GOOD |  | ANY
20220380000300 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000301 | 3.6 | preliminary metrology | [5 empty] | AA1 | OK |  | SPARE |  | B5/B6
20220380000302 | 2.1 | preliminary metrology | [5 empty] | AA1 | negative |  | PASS |  | ANY
20220380000303 | 1.2 | [6 empty] | AA1 | OK |  | GOOD |  | B5/B6
20220380000304 | 3.3 | [6 empty] | AA1 | OK |  | PASS2 |  | ANY
20220380000305 | 1.1 | [6 empty] | AA1 | negative |  | GOOD |  | ANY
20220380000306 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000307 | 1.2 | [6 empty] | AA1 | OK |  | GOOD |  | B5/B6
20220380000308 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000309 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000310 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000311 | 1.1 | preliminary metrology | [5 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000312 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000313 | 3.3 | [6 empty] | AA1 | OK |  | PASS2 |  | ANY
20220380000314 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000315 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000316 | 3.65 | [6 empty] | AA1 | OK |  | SPARE |  | B6
20220380000317 | 1.1 | [6 empty] | AA1 | negative |  | GOOD |  | ANY
20220380000318 | 1.1 | [6 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000319 | 1.1 | preliminary metrology | [5 empty] | AA1 | OK |  | GOOD |  | ANY
20220380000320 | 3.65 | [6 empty] | AA1 | OK |  | SPARE |  | B6
20220380000321 | [7 empty] | AA1
20220380000322 | [7 empty] | AA1
20220380000323 | 1.1 | [7 empty] | negative |  | GOOD |  | ANY
20220380000324 | 2.1 | [6 empty] | AA1 | OK |  | PASS |  | ANY