## Introduction
Barrel Modules Status
Version history | date (yyyy/mm/dd)
1st version | 2003-07-03
1.1 | 2003-07-24
1.2 | 2003-07-29 | updates in Inventory, Pipeline, forB5B6, HOLD, REWORK, s-curves sheets
1.3 | 2003-07-31 | update in Pipeline sheet, add FAIL sheet
1.4 | 2003-08-01 | update in Pipeline, Inventry sheet
1.5 | 2003-08-01 | update in Pipeline (wording, and formula in column I), HOLD (split SB and Module), FAIL, ASICstuffing sheets
1.6 | 2003-08-19 | update in Scurves (wording, >0.4fC), ASICstuffing, ASICyield(formula), add Location sheet, print area
1.7 | 2003-08-26 | update in Categories sheet (listing sums of GOOD+PASS for barrels)
1.8 | 2003-11-05 | correction of mistypo in categories definition, module for B3 and B4, temperature... <2 deg.C
1.9 | 2004-01-07 | add columns of STUCKCELL>2/link and BHN (block of high noise = partbonded in hybrid) at SDF=0.4, and modify counting of total , in ASICdefects sheet
2.0 | 2004-01-19 | add Quality and Sign-off columns in "Location" sheet. Sign-off "Category" is either of GOOD/PASS/FAIL.
2.1 | 2004-01-20 | add "Electrical special setting" in Quality columns in "Location" sheet
2.2 | 2004-02-05 | calculate "Modules classifed" in Pipeline from Categories
2.2.1 | 2004-02-23 | update Introduction sheet on description of HOLD sheet
2.3.1 | 2004-04-21 | update to include PASS2, SPARE, FAIL catogories defined in March 2004 SCT meeting and after
2.3.2 | 2004-04-26 | refined the MDM decay fitting function to account for the plateau current
2.3.3 | 2004-05-07 | update the hybrid metrology parameters for PASS etc. + revive HOLD columns for compatibility+ number of bug fixes
2.3.4 | 2004-05-14 | update PASS2/SPARE of hymxf(b), hymyf(b), and conp1y + add temp. diff. dT>4 deg.C for SPARE + bug fix + consistent s-curves >0.45 fC
2.4.1 | 2004-07-21 | after the June SCT week, creation of B6 PASS2 category (MD>300V, Vdd min<=3.8V), B6 (2<=dT<4), B5 (dT<2), and hymxf/hymyf/hymxb/hymyb<500um for PASS2
Barrel Module Categories
"SB" is the sensor-baseboard sandwich WITHOUT hybrid
"Module" is the final object, I.e., SB fitted WITH hybrid
When counted, SB's and Modules are exclusive each other.
Also, the entries in 1.1, 1.2, ..., are exclusive each other.
1 | GOOD
Fully completed and tested module, satisfying all specifications (mechanical and electrical).
For electrical performance, it is expected that the large majority of modules will have considerably less than the 1% bad channels of the specification.
Within Good are the subcategories:
1.1 | Good for any barrel
1.2 | Use only for barrel 5 or 6
1.25 | For barrel 6
(See separate proposal for these subcategories)
2 | PASS
The module just misses satisfying one or more of the mechanical specifications.
The purpose of the category is to keep modules in the tails of the expected mechanical distributions.
The number of Pass modules should therefore be much less than the number of Good modules.
A Pass module must still fully satisfy the electrical specification.
Pass modules are agreed to be usable in ATLAS, without further discussion.
Within Pass are the subcategories:
2.1 | Pass for any barrel
2.2 | Use only for barrel 5 or 6
2.25 | For barrel 6
The limits of quantities as measured for the Pass category: see the attached table
3 | HOLD
(This category is kept for historical reasons, and the entries are subtracted once the entries are classified in PASS2 or SPARE's.)
These are modules outside one or more of the Pass limits.
They are stopped in production at the point they are found to be outside the limit (ie a hybrid is not fitted if the baseboard-sensor sandwich is outside "pass" metrology values).
They are carefully stored for later assessment by the Barrel Module community.
3.1 | SB's
3.2 | Modules (I.e., SB with hybrid)
(e.g., I>4uA at 500V without Microdischarge(MD), MD<350V, Abnormally long current decay , lost channels>7/side, >15/total, etc)
3.3, 3.4 | PASS2
A wider (about 20% more than PASS) metrology cut parameters. The cut parameters are listed below
To be mated with hybrids with AA1 chips as much as possible
These are to be used in an EMERGENCY case in ATLAS
Within PASS2 are the subcategories:
3.3 | For any barrels
3.4 | For barrel 5 or 6
3.45 | For barrel 6
3.5, 3.6 | SPARE
Those that metrology is worse than PASS2, or if the electrical properties are out of spec. Fill the reasons in the SPARE sheet (see below)
These are to be used in an EXTREME EMERFGENCY case in ATLAS
To be mated with hybrids with AA1 chips as much as possible
Within SPARE are the subcategories:
3.5 | For any barrels
3.6 | For barrel 5 or 6
3.65 | For barrel 6
4 | FAIL
Modules that could never go in ATLAS,
for example broken or badly scratched detectors, gross mechanical errors (such as glue coming out), many bad channels due to bonding problems, broken ASICs that can't be replaced.
and out of SPARE limits
4.1 | SB's | (A FAIL S/B would not have a hybrid added to it)
4.2 | Modules (I.e., SB with hybrid)
5 | REWORK modules
Modules held back for rework that might make them usable,
e.g., replacing an ASIC, gluing on a replacement pitch adapter, re-bonding work.
6 | Classified
This "Classified" column is the sum of the above exclusive columns, in order to have the total number of classified SB and modules
First proposals for Modules to Select for Barrels 3 and 4
1 | Series (not pre-series) detectors.
2 | No sign of IV 'microdischarge' up to 500V bias (in nitrogen or dry air atmosphere)
3 | No history of unexplained bad IV behaviour (eg current very big on first test of module)
5 | No bad visual inspection features that could relate to HV robustness
(eg unusual amount of debris/marks near detector edges, messy detector-detector bonding that leaves any bonds flat near detector surface, broken bits of bond wire, etc.)
6 | Thermistor temperatures are as expected for test setup and difference in their temperature(dT) is dT<2 deg C
7 | Cooling facing b-angle within specification (I.e., <3 mrad)
8 | Any conclusions on irradiation hardness that might be established in future
Amendaments on 2004/06/28 (yyyy/mm/dd)
a1 | Thermistor temperatures difference dT< 2 degC for B3,B4,B5, and 2<=dT<4 deg.C for B6
a2 | Microdischarge (MD), MD>300V for B6, >350V for B5, and >500V for B3 and B4
a3 | Vdd for Bypass test, Vdd min = 3.5V for any barrel and Vdd min <=3.8V for B6
Barrel classification
|  |  | B3/B4 | B5/B6 | B6
1 | Pre-series sensors |  | No | Yes | <-
2 | MD>350V |  | >500V | >=350V | >=300V
3 | Bad current behaviour |  | No | Yes | <-
5 | Bad visual features |  | No | Yes | <-
6 | Thermistor T diff.>=2C |  | <2 degC | <- | 2<=dT<4 degC
7 | b angle >3 mrad |  | <=3 mrad | >3 mrad | <-
8 | Irradiation aspects
9 | Vdd min |  | 3.5V | <- | 3.5V< <=3.8V
Metrology parameters
(Measurement values are rounded down for classification)
|  | Parameter | GOOD | PASS | PASS2 | SPARE | FAIL
|  | mhx [um] | +/-30 | +/-40 | +/-50 | +/-60 | > +/-60
|  | mhy [um] | +/-30 | +/-40 | +/-50 | +/-60 | > +/-60
|  | msx [um] | +/-100 | +/-140 | +/-170 | +/-200 | > +/-200
|  | msy [um] | +/-30 | +/-40 | +/-50 | +/-60 | > +/-60
|  | sepf [um] | +/-10 | +/-20 | +/-30 | +/-40 | > +/-40
|  | sepb [um] | +/-10 | +/-20 | +/-30 | +/-40 | > +/-40
|  | midxf [um] | +/-10 | +/-20 | +/-30 | +/-40 | > +/-40
|  | midyf [um] | +/-5 | +/-8 | +/-10 | +/-15 | > +/-15 | exclusive of stereo
|  | a1 [mrad] | +/-0.13 | <- | +/-0.16 | +/-0.24 | > +/-0.24
|  | a2 [mrad] | +/-0.13 | <- | +/-0.16 | +/-0.24 | > +/-0.24
|  | a3 [mrad] | +/-0.13 | <- | +/-0.16 | +/-0.24 | > +/-0.24
|  | a4 [mrad] | +/-0.13 | <- | +/-0.16 | +/-0.24 | > +/-0.24
|  | stereo [mrad] | +/-0.13 | <- | +/-0.16 | +/-0.24 | > +/-0.24 | exclusive of midyf
|  | hymxf [um] | +/-100 | +/-200 | +/-500 | <- | >+/-500
|  | hymyf [um] | +/-100 | +/-200 | +/-500 | <- | >+/-500
|  | hymaf [mrad] | +/-3.145 | +/-3.145 | +/-6.290 | <- | >+/-6.290
|  | hymxb [um] | +/-100 | +/-200 | +/-500 | <- | >+/-500
|  | hymyb [um] | +/-100 | +/-200 | +/-500 | <- | >+/-500
|  | hymab [mrad] | +/-3.145 | +/-3.145 | +/-6.290 | <- | >+/-6.290
|  | conp1x [um] | +/-320 | +/-480 | +/-640 | <- | >+/-640
|  | conp1y [um] | +/-100 | +/-200 | +/-300 | <- | >+/-300
|  | maxZlower [mm] | -0.2 | <- | <- | <- | <-0.2 | absolute envelope
|  | maxZupper [mm] | 0.2 | <- | <- | <- | >0.2 | absolute envelope
|  | moduleThickness [mm] | 0.1 | <- | 0.15 | 0.2 | >0.2 | 1-sided
|  | optimalMaxZerrorLower [mm] | 0.05 | 0.07 | 0.09 | 0.11 | >0.11
|  | optimalMaxZerrorUpper [mm] | 0.05 | 0.07 | 0.09 | 0.11 | >0.11
|  | optimalRMSZerrorLower [mm] | 0.025 | <- | 0.03 | 0.03 | >0.03
|  | optimalRMSZerrorUpper [mm] | 0.025 | <- | 0.03 | 0.03 | >0.03
|  | loCoolingFacing a [mrad] | +/-0.5 | <- | +/-0.6 | +/-0.6 | >+/-0.6
|  | b [mrad] | +/-3 | +/-5 | +/-6 | +/-7 | >+/-7
|  | loCoolingFacingConcavity [mm] | +/-0.03 | <- | +/-0.04 | +/-0.05 | >+/-0.05
|  | capMaxThickness [mm] | 6.44 | <- | <- | <- | >6.44 | absolute envelope
|  | hyb1NearH [mm] | +/-0.19 | +/-0.25 | +/-0.35 | <- | >+/-0.35 | average= (hyb1LeftNearH+hyb1RightNearH)/2
|  | hyb1FarH[mm] | +/-0.19 | +/-0.25 | +/-0.35 | <- | >+/-0.35 | average= (hyb1LeftFarH+hyb1RightFarH)/2
|  | hyb2NearH [mm] | +/-0.19 | +/-0.25 | +/-0.35 | <- | >+/-0.35 | average= (hyb2LeftNearH+hyb2RightNearH)/2
|  | hyb2FarH [mm] | +/-0.19 | +/-0.25 | +/-0.35 | <- | >+/-0.35 | average= (hyb2LeftFarH+hyb2RightFarH)/2
|  | hyb1Concavity [mm] | +/-0.15 | +/-0.25 | +/-0.35 | <- | >+/-0.35
|  | hyb2Concavity [mm] | +/-0.15 | +/-0.25 | +/-0.35 | <- | >+/-0.35
|  | hyb1CapMaxH [mm] | 0.3 | <- | <- | <- | >0.3 | absolute envelope
|  | hyb2CapMaxH [mm] | 0.3 | <- | <- | <- | >0.3 | absolute envelope
|  | hybridMaxThickness [mm] | 0.44 | <- | <- | <- | >0.44 | absolute envelope
"exclusive": e.g., if midyf is in SPARE cut, the stereo must be below or equal to the next tightest cut, i.e., PASS2 cut
Electrical parameters
|  | Parameter | GOOD | <- | PASS2 | SPARE | FAIL
|  | I-V (No MD)[uA] | <=4@500V | <- | <- | <=4@350V | >4@350V
|  | Microdischarge onset voltage [V] | >=350 | <- | >=300 | >=150 | <150
|  | Microdischarge decay time (MDM) [hr] | <=1 | <- | <- | <=6 | >6
|  | Microdischarge decay plateau current [uA] | <=1 | <- | <- | <=4 | >4
|  | Number of lost channels (sideconsective, total) | <=7,<=15 | <- | <=10,<=20 | <=14,<=30 | >14, >30
|  | Bad S-curves >0.45fC | <=0.45fC | <- | <- | >0.45fC | ---
|  | Thermistor temp. diff. dT [deg.C] | <=4 | <- | <- | >4 | ---
|  | Vdd min. [V] | 3.5V | <- | 3.5V< <=3.8V | >3.8V | ---
Definition of MDM decay timeT: fit { I(t)=(I(0)-I(plateau))*exp(-t/T)+I(plateau) } to the decay part,
and approximately the time when { I(T)-I(plateau)}/{I(0)-I(plateau)}=1/2.7
Pipeline sheet:
1 | SB(Sensor-baseboard) started
2 | SB's sent/ready for classification
3 | SB's classified
4 | SB's sent/ready for hybrid mounting (="SB's classified" - ("SB's HOLD" + "SB's FAIL" in "Categories"))
5 | Modules sent/ready for wire-bonding (I.e., hybrid mounting completed = "SB's ready for hybrid mounting" - "Modules in progress at SB stage on date")
6 | Modules sent/ready for classification (I.e., wire-bonding completed)
7 | Modules classified (= "Classifed" - ("SB's HOLD"+"SB's FAIL") in "Categories")
- | Calculation/given | Modules in progress at SB stage on date(="SB's sent/ready for hybrid mounting" - "Modules sent/ready for wire-bonding")
- | Calculation/given | Modules in progress with hybrid mounted on date(="Modules sent/ready for wire-bonding" - "Modules classified")
Categories sheet:
1.1 | GOOD | for any barrel
1.2 |  | for B5/B6
1.25 |  | for B6
2.1 | PASS | for any barrel
2.2 |  | for B5/B6
2.25 |  | for B6
3.1 | (HOLD) | (SB's)
3.2 |  | (Modules)
3.3 | PASS2 | for any barrel
3.4 |  | for B5/B6
3.45 |  | B6
3.5 | SPARE | for any barrel |  | (If a module can not be assigned to one of "any barrel", "B5/B6", or "B6", it will go to 4.2 FAIL Modules)
3.6 |  | for B5/B6
3.65 |  | B6
4.1 | FAIL | SB's
4.2 |  | Modules
5 | REWORK | Modules
HOLD sheet: | Obsolete, but fill those SB and Modules if they are not yet classified into PASS2 or SPARE's
1 | SB out of PASS limits
2 | SB Others
3 | Module out of PASS limits
4 | I(500V)>4uA without microdischarge (MD<350) without annealing
5 | MD<350V
6 | Abnormally long current decay at 500V, >1hr
7 | Lost channels >7consective/side, >15/total
8 | Bad s-curves >0.45fC
9 | Others
for B5B6 sheet:
GOOD+PASS
1 | Pre-series sensors
2 | MD>=350V
3 | Bad current behaviour
5 | Bad visual features
6 | Thermistor T diff.>=2C
7 | b angle >3 mrad
8 | Irradiation aspects
PASS2+SPARE
11 | Pre-series sensors
12 | MD>=350V
13 | Bad current behaviour
15 | Bad visual features
16 | Thermistor T diff.>=2C
17 | b angle >3 mrad
18 | Irradiation aspects
for B6 sheet:
1 | MD>=300V
2 | Thermistor T diff >=2C
3 | 3.5V< Vdd min <= 3.8V
4 | Others
SPARE sheet:
1 | Metrology out of PASS2 (and inside of SPARE) limits
2 | I(350V)>4uA without microdischarge (MD<350) without annealing
3 | 150V<=MD<350V
4 | Abnormally long MD current decay , 1hr < decay time <= 6 hr, or high MD plateau current, 1uA< I_MD<=4 uA
5 | Lost channels, 10< consective/side<=14, 20< total <=30
6 | Bad s-curves >0.45fC
7 | Thermmistor temp diff dT>4 deg.C
8 | Bypass test Vdd min >3.8V
9 | Others
FAIL sheet:
1 | SB | Sensor damaged
2 | SB | BB damaged
3 | SB | Gross mechanical error (e.g. metrology out of SPARE limits, glue coming out)
4 | SB | Others
5 | Module | Sensor damaged
6 | Module | BB damaged
7 | Module | Gross mechanical error (e.g. metrology out of SPARE limits)
8 | Module | Abnormal leakge current (see Electrical Parameters limits)
9 | Module | Too many bad channels (see Electrical Parameters limits)
10 | Module | ASIC's non-replaceable
11 | Module | No assignable barrel
12 | Module | Others
REWORK sheet:
Modules are requiring further actions:
1 | replacing an ASIC
2 | replacing a pitch adaper
3 | rebonding wires
4 | replacing hybrid
5 | replacing connector
6 | further visual inspection
7 | cleaning
8 | others
Location sheet:
| Module id |  | First 7 digits can be automated with B3 cell
| Categories |  | 1.1~5 | Mandatory to be filled that automatically fills "Category" and "Barrel assignment" cells
Module location/usage
| Date |  | (dd/mm/yyyy) | Date of filling the row
| I-V |  | GOOD/PASS2/SPARE/FAIL
| I-V |  | Comment
| Electrical |  | GOOD/PASS2/SPARE/FAIL
| Electrical Special Setting |  | ISH=20, SDF=0.4
| Electrical |  | Comment
| S-curves Category |  | (ok(good) /negative /positive />0.45) |  |  | for good, "-": wiggle in negative threshold, "+": wiggles in both negative and positive threaholds, ">0.45": wiggles threshold > 0.45fC
| S-curves |  | Comment
| Category |  | GOOD/PASS/PASS2/SPARE/FAIL/REWORK, automatically filled from the "Categories" value
Reason for HOLD/FAIL
| Barrel assignment |  | Any/B5B6, automatically filled from the "Categories" value
Reason for B5B6
Sign-off comment

## Pipeline
Cluster | UKB
Pipeline | ("sent" means either sent or ready to be sent)
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Cumulative
Date (yymmdd) | SB's started | SB's sent/ready for classification | SB's classified | SB's sent/ready for hybrid mounting | Modules sent/ready for wire-bonding | Modules sent/ready for classification | Modules classified | Modules in progress at SB stage on date (=(4)-(5)) | Modules in progress with hybrid mounted on date(=(5)-(7))
030501 | 132 | 132 | 145 | 135 | 120 | 87 | 87 | 15 | 33
030601 | 180 | 180 | 179 | 169 | 135 | 118 | 118 | 34 | 17
030701 | 228 | 228 | 229 | 217 | 138 | 131 | 131 | 79 | 7
030801 | 275 | 275 | 275 | 262 | 142 | 131 | 131 | 120 | 11
030901 | 287 | 287 | 287 | 274 | 150 | 142 | 142 | 124 | 8
031001 | 345 | 345 | 355 | 338 | 178 | 154 | 154 | 160 | 24
031101 | 400 | 400 | 395 | 377 | 216 | 201 | 201 | 161 | 15
031201 | 440 | 440 | 439 | 420 | 226 | 223 | 223 | 194 | 3
040101 | 441 | 441 | 441 | 422 | 236 | 235 | 235 | 186 | 1
040201 | 491 | 491 | 490 | 471 | 270 | 256 | 256 | 201 | 14
040301 | 536 | 536 | 531 | 510 | 322 | 307 | 307 | 188 | 15
040401 | 587 | 587 | 587 | 566 | 373 | 363 | 363 | 193 | 10
040501 | 632 | 632 | 632 | 611 | 418 | 408 | 408 | 193 | 10
040601 | 674 | 674 | 674 | 659 | 466 | 447 | 447 | 193 | 19
040701 | 708 | 708 | 708 | 693 | 524 | 518 | 518 | 169 | 6
040801 | 708 | 708 | 708 | 693 | 599 | 543 | 543 | 94 | 56
040901 | 708 | 708 | 708 | 693 | 660 | 607 | 607 | 33 | 53
041001 | 708 | 708 | 708 | 694 | 691 | 677 | 677 | 3 | 14
041101 | 708 | 708 | 708 | 704 | 704 | 701 | 701 | 0 | 3
041201 | 708 | 708 | 708 | 704 | 704 | 704 | 704 | 0 | 0
050101 | 708 | 708 | 708 | 704 | 704 | 704 | 704 | 0 | 0
050201 | 708 | 708 | 708 | 704 | 704 | 704 | 704 | 0 | 0

## Categories
Cluster | UKB
Module categories (each column entry is exclusive each other)
| 1.1 | 1.2 | 1.25 | 2.1 | 2.2 | 2.25 | 3.1 | 3.2 | 3.3 | 3.4 | 3.45 | 3.5 | 3.6 | 3.65 | 4.1 | 4.2 | 5 | 6
Cumulative | GOOD |  |  | PASS |  |  | (HOLD) |  | PASS2 |  |  | SPARE |  |  | FAIL |  | REWORK |  | GOOD+PASS |  |  |  | YIELD
Date (yymmdd) | for any barrel | for B5/B6 | for B6 | for any barrel | for B5/B6 | forB6 | (SB's) | (Modules) | for any barrel | for B5/B6 | for B6 | for any barrel | for B5/B6 | for B6 | SB's | Modules | Modules | Classified | for any barrel | for B5/B6 | forB6 | total | PASS /(GOOD+PASS) | (GOOD+PASS) /Classified | (HOLD) /Classified | PASS2 /Classified | SPARE /Classified | FAIL /Classified | REWORK /Classified
030501 | 50 | 17 |  | 5 | 0 |  | 7 | 8 | 0 | 0 |  | 0 | 0 |  | 3 | 1 | 6 | 97 | 55 | 17 | 0 | 72 | 6.944% | 74.23% | 15.46% | 0% | 0% | 4.124% | 6.186%
030601 | 69 | 21 |  | 5 | 3 |  | 7 | 12 | 0 | 0 |  | 0 | 0 |  | 3 | 2 | 6 | 128 | 74 | 24 | 0 | 98 | 8.163% | 76.56% | 14.84% | 0% | 0% | 3.906% | 4.688%
030701 | 76 | 27 |  | 5 | 3 |  | 9 | 12 | 0 | 0 |  | 0 | 0 |  | 3 | 2 | 6 | 143 | 81 | 30 | 0 | 111 | 7.207% | 77.62% | 14.69% | 0% | 0% | 3.497% | 4.196%
030801 | 76 | 27 |  | 5 | 3 |  | 9 | 12 | 0 | 0 |  | 0 | 0 |  | 4 | 2 | 6 | 144 | 81 | 30 | 0 | 111 | 7.207% | 77.08% | 14.58% | 0% | 0% | 4.167% | 4.167%
030901 | 83 | 30 |  | 6 | 3 |  | 9 | 12 | 0 | 0 |  | 0 | 0 |  | 4 | 2 | 6 | 155 | 89 | 33 | 0 | 122 | 7.377% | 78.71% | 13.55% | 0% | 0% | 3.871% | 3.871%
031001 | 90 | 32 |  | 8 | 3 |  | 11 | 13 | 0 | 0 |  | 0 | 0 |  | 6 | 2 | 6 | 171 | 98 | 35 | 0 | 133 | 8.271% | 77.78% | 14.04% | 0% | 0% | 4.678% | 3.509%
031101 | 123 | 40 |  | 12 | 5 |  | 11 | 13 | 0 | 0 |  | 0 | 0 |  | 7 | 2 | 6 | 219 | 135 | 45 | 0 | 180 | 9.444% | 82.19% | 10.96% | 0% | 0% | 4.11% | 2.74%
031201 | 138 | 43 |  | 12 | 6 |  | 11 | 15 | 0 | 0 |  | 0 | 0 |  | 8 | 4 | 5 | 242 | 150 | 49 | 0 | 199 | 9.045% | 82.23% | 10.74% | 0% | 0% | 4.959% | 2.066%
040101 | 146 | 45 |  | 12 | 6 |  | 11 | 17 | 0 | 0 |  | 0 | 0 |  | 8 | 4 | 5 | 254 | 158 | 51 | 0 | 209 | 8.612% | 82.28% | 11.02% | 0% | 0% | 4.724% | 1.969%
040201 | 160 | 49 |  | 13 | 7 |  | 11 | 17 | 0 | 0 |  | 0 | 0 |  | 8 | 4 | 6 | 275 | 173 | 56 | 0 | 229 | 8.734% | 83.27% | 10.18% | 0% | 0% | 4.364% | 2.182%
040301 | 186 | 69 |  | 16 | 9 |  | 11 | 16 | 0 | 0 |  | 0 | 0 |  | 10 | 4 | 7 | 328 | 202 | 78 | 0 | 280 | 8.929% | 85.37% | 8.232% | 0% | 0% | 4.268% | 2.134%
040401 | 227 | 77 |  | 17 | 10 |  | 11 | 20 | 0 | 0 |  | 0 | 0 |  | 10 | 4 | 8 | 384 | 244 | 87 | 0 | 331 | 8.157% | 86.2% | 8.073% | 0% | 0% | 3.646% | 2.083%
040501 | 257 | 83 |  | 18 | 11 |  | 10 | 26 | 0 | 0 |  | 0 | 0 |  | 11 | 5 | 8 | 429 | 275 | 94 | 0 | 369 | 7.859% | 86.01% | 8.392% | 0% | 0% | 3.73% | 1.865%
040601 | 278 | 100 |  | 24 | 6 |  | 0 | 0 | 2 | 0 |  | 0 | 20 |  | 15 | 9 | 8 | 462 | 302 | 106 | 0 | 408 | 7.353% | 88.31% | 0% | 0.4329% | 4.329% | 5.195% | 1.732%
040701 | 325 | 93 |  | 27 | 8 |  | 0 | 0 | 7 | 3 | 23 | 0 | 17 |  | 15 | 8 | 7 | 533 | 352 | 101 | 0 | 453 | 7.726% | 84.99% | 0% | 6.191% | 3.189% | 4.315% | 1.313%
040801 | 336 | 84 | 26 | 26 | 10 | 2 | 0 | 0 | 8 | 3 | 9 | 4 | 21 | 1 | 15 | 8 | 5 | 558 | 362 | 94 | 28 | 484 | 7.851% | 86.74% | 0% | 3.584% | 4.659% | 4.122% | 0.8961%
040901 | 361 | 96 | 30 | 28 | 12 | 2 | 0 | 0 | 8 | 4 | 18 | 4 | 21 | 3 | 15 | 15 | 5 | 622 | 389 | 108 | 32 | 529 | 7.94% | 85.05% | 0% | 4.823% | 4.502% | 4.823% | 0.8039%
041001 | 399 | 103 | 32 | 31 | 11 | 5 | 0 | 0 | 10 | 5 | 27 | 5 | 21 | 4 | 14 | 19 | 5 | 691 | 430 | 114 | 37 | 581 | 8.09% | 84.08% | 0% | 6.078% | 4.342% | 4.776% | 0.7236%
041101 | 406 | 110 | 33 | 31 | 12 | 5 | 0 | 0 | 16 | 7 | 29 | 5 | 22 | 4 | 4 | 21 | 0 | 705 | 437 | 122 | 38 | 597 | 8.04% | 84.68% | 0% | 7.376% | 4.397% | 3.546% | 0%
041201 | 406 | 110 | 33 | 31 | 12 | 5 | 0 | 0 | 16 | 7 | 29 | 5 | 22 | 4 | 4 | 24 | 0 | 708 | 437 | 122 | 38 | 597 | 8.04% | 84.32% | 0% | 7.345% | 4.379% | 3.955% | 0%
050101 | 406 | 110 | 33 | 31 | 12 | 5 | 0 | 0 | 16 | 7 | 29 | 5 | 22 | 4 | 4 | 24 | 0 | 708 | 437 | 122 | 38 | 597 | 8.04% | 84.32% | 0% | 7.345% | 4.379% | 3.955% | 0%
050201 | 406 | 110 | 33 | 31 | 12 | 5 | 0 | 0 | 16 | 7 | 29 | 5 | 22 | 4 | 4 | 24 | 0 | 708 | 437 | 122 | 38 | 597 | 8.04% | 84.32% | 0% | 7.345% | 4.379% | 3.955% | 0%

## forB5B6
Cluster | UKB
Modules for B5/B6
Reasons:
| GOOD+PASS | [6 empty] | PASS2+SPARE
Cumulative | 1 | 2 | 3 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 15 | 16 | 17 | 18
Date (yymmdd) | Pre-series sensors | MD>=350V | Bad current behaviour | Bad visual features | Thermistor T diff.>=2C | b angle >3 mrad | Irradiation aspects | Pre-series sensors | MD>=350V | Bad current behaviour | Bad visual features | Thermistor T diff.>=2C | b angle >3 mrad | Irradiation aspects
030501 | 0 | 13 | 1 | 0 | 2 | 0 | 0
030601 | 0 | 15 | 6 | 0 | 2 | 0 | 0
030701 | 0 | 16 | 10 | 0 | 2 | 0 | 0
030801 | 0 | 16 | 10 | 0 | 2 | 0 | 0
030901 | 0 | 21 | 10 | 0 | 2 | 0 | 0
031001 | 0 | 23 | 10 | 0 | 2 | 0 | 0
031101 | 0 | 28 | 13 | 0 | 2 | 2 | 0
031201 | 0 | 29 | 14 | 0 | 2 | 2 | 0
040101 | 0 | 31 | 14 | 0 | 2 | 2 | 0
040201 | 0 | 32 | 16 | 0 | 2 | 2 | 0
040301 | 0 | 42 | 16 | 0 | 2 | 2 | 0
040401 | 0 | 52 | 18 | 0 | 13 | 4 | 0
040501 | 0 | 61 | 18 | 0 | 11 | 4 | 0
040601 | 0 | 66 | 23 | 0 | 13 | 4 | 0
040701 | 0 | 71 | 24 | 0 | 0 | 5 | 0
040801 | 0 | 66 | 23 | 0 |  | 5 | 0
040901 | 0 | 72 | 26 | 0 |  | 6 | 0
041001 | 0 | 78 | 30 | 0 |  | 6 | 0
041101 | 0 | 83 | 32 | 0 |  | 5 | 0
041201 | 0 | 83 | 32 | 0 |  | 5 | 0
050101 | 0 | 83 | 32 | 0 |  | 5 | 0
050201 | 0 | 83 | 32 | 0 |  | 5 | 0

## forB6
Cluster | UKB
Modules for B6
Reasons:
Cumulative | 1 | 2 | 3 | 4
Date (yymmdd) | MD>=300V | Thermistor T diff.>=2C | Vdd min 3.5V< <=3.8V | Others
030501
030601
030701
030801
030901
031001
031101
031201
040101
040201
040301
040401
040501
040601
040701
040801 | 12 | 25 | 1
040901 | 3 | 29 | 0
041001 | 18 | 32 | 15
041101 | 20 | 32 | 16
041201 | 20 | 32 | 16
050101 | 20 | 32 | 16
050201 | 20 | 32 | 16

## HOLD
Cluster | XXX
SB or Modules in HOLD (This sheet is kept for historical reason)
Reasons:
| SB |  | Module
Cumulative | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Date (yymmdd) | Out of PASS limits | Others | Out of PASS limit | I(500V)>4uA W/O MD<350V | MD<350V | Abnormally long current decay, >1hr | Lost ch. >7consective/side, >15/total | Bad s-curves >0.45fC | Others
030501 | 7 |  | 3 | 0 | 4 | 0 | 0 | 0 | 1
030601 | 7 |  | 3 | 0 | 7 | 0 | 0 | 0 | 2
030701 | 9 |  | 3 | 0 | 7 | 0 | 0 | 0 | 2
030801 | 10 |  | 3 | 0 | 7 | 0 | 0 | 0 | 2
030901 | 10 |  | 3 | 0 | 7 | 0 | 0 | 0 | 2
031001 | 11 |  | 3 | 0 | 8 | 0 | 0 | 0 | 2
031101 | 11 |  | 3 | 0 | 8 | 0 | 0 | 0 | 2
031201 | 11 |  | 3 | 1 | 8 | 0 | 0 | 0 | 3
040101 | 11 |  | 3 | 2 | 9 | 0 | 0 | 0 | 3
040201 | 11 |  | 3 | 1 | 9 | 0 | 0 | 0 | 3
040301 | 11 |  | 3 | 1 | 10 | 0 | 0 | 0 | 1
040401 | 11 |  | 4 | 3 | 11 | 0 | 0 | 0 | 2
040501 | 10 |  | 4 | 3 | 12 | 0 | 0 | 0 | 7
040601 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
040701 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
040801 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
040901 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
041001 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
041101 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
041201 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
050101 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
050201 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SPARE
Cluster | UKB
SB or Modules in SPARE
Reasons:
Module
Cumulative | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Date (yymmdd) | Metrology out of PASS2 (and inside of SPARE) limits | I(350V)>4uA without micro discharge (MD<350) without annealing | 150V<=MD<350V | Long MD current decay , 1hr < decay time <= 6 hr | Lost channels, 10< consective /side<=14, 20< total <=30 | Bad s-curves >0.45fC | Thermistor temp diff dT>4 deg.C | Bypass test Vdd min >3.8V | Others
030501
030601
030701
030801
030901
031001
031101
031201
040101
040201
040301
040401
040501
040601 | 0 | 3 | 10 | 1 | 0 | 0 | 6 | 0 | 0
040701 | 0 | 3 | 8 | 0 | 0 | 0 | 6 | 0 | 0
040801 | 0 | 3 | 9 | 0 | 4 | 0 | 6 | 0 | 4
040901 | 0 | 3 | 11 | 0 | 4 | 0 | 6 | 0 | 4
041001 | 0 | 3 | 12 | 0 | 5 | 0 | 6 | 0 | 4
041101 | 0 | 3 | 12 | 0 | 6 | 0 | 6 | 4
041201 | 0 | 3 | 12 | 0 | 6 | 0 | 6 | 4
050101 | 0 | 3 | 12 | 0 | 6 | 0 | 6 | 4
050201 | 0 | 3 | 12 | 0 | 6 | 0 | 6 | 4

## FAIL
Cluster | UKB
SB or Modules in FAIL
Reasons:
| SB |  |  |  | Module
Cumulative | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Date (yymmdd) | Sensor damaged | BB damaged | Gross mechanical error (e.g. metrology out of SPARE limits, glue coming out) | Others | Sensor damaged | BB damaged | Gross mechanical error (e.g. metrology out of SPARE limits) | Abnormal leakge current (see Electrical Parameters limits) | Too many bad channels (see Electrical Parameters limits) | ASIC's non-replaceable | No assignable barrel | Others
030501 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
030601 | 0 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
030701 | 0 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
030801 | 0 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
030901 | 0 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
031001 | 0 | 1 | 0 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
031101 | 0 | 1 | 0 | 6 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
031201 | 0 | 1 | 0 | 7 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2
040101 | 0 | 1 | 0 | 7 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2
040201 | 0 | 1 | 0 | 7 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2
040301 | 0 | 1 | 1 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2
040401 | 0 | 1 | 1 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2
040501 | 0 | 1 | 1 | 9 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 2
040601 | 0 | 1 | 5 | 9 | 3 | 0 | 5 | 0 | 0 | 0 | 0 | 1
040701 | 0 | 1 | 5 | 9 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 1
040801 | 0 | 1 | 5 | 9 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 1
040901 | 0 | 1 | 5 | 9 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 8
041001 | 0 | 1 | 5 | 9 | 5 | 0 | 4 | 1 | 0 | 0 | 0 | 3
041101 | 0 | 1 | 3 | 0 | 5 | 1 | 7 | 3 | 1 | 0 | 0 | 4
041201 | 0 | 1 | 3 | 0 | 5 | 1 | 7 | 3 | 4 | 0 | 0 | 4
050101 | 0 | 1 | 3 | 0 | 5 | 1 | 7 | 3 | 4 | 0 | 0 | 4
050201 | 0 | 1 | 3 | 0 | 5 | 1 | 7 | 3 | 4 | 0 | 0 | 4

## REWORK
Cluster | UKB
Modules in REWORK
Reasons: requiring ...
Cumulative | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Date (yymmdd) | replacing ASIC | replacing PA | rebonding wires | replacing hybrid | replacing connector | further visual inspection | cleaning | others
030501 | 1 | 1 | 0 | 0 | 0 | 4 | 0 | 0
030601 | 1 | 1 | 0 | 0 | 0 | 4 | 0 | 0
030701 | 1 | 1 | 0 | 0 | 0 | 4 | 0 | 0
030801 | 1 | 1 | 0 | 0 | 0 | 4 | 0 | 0
030901 | 1 | 1 | 0 | 0 | 0 | 4 | 0 | 0
031001 | 1 | 1 | 0 | 0 | 0 | 4 | 0 | 0
031101 | 1 | 1 | 0 | 0 | 0 | 3 | 0 | 0
031201 | 1 | 1 | 0 | 0 | 0 | 3 | 0 | 0
040101 | 1 | 1 | 0 | 0 | 0 | 4 | 0 | 0
040201 | 1 | 1 | 0 | 0 | 0 | 3 | 0 | 1
040301 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 2
040401 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 2
040501 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 2
040601 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 2
040701 | 2 | 1 | 0 | 0 | 0 | 4 | 0 | 0
040801 | 2 | 1 | 0 | 0 | 0 | 2 | 0 | 0
040901 | 2 | 1 | 0 | 0 | 0 | 2 | 0 | 0
041001 | 2 | 1 | 0 | 0 | 0 | 2 | 0 | 0
041101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
041201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
050101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
050201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Scurves
Cluster | UKB
S-curve wiggles in Noise-Occupancy plots in modules (GOOD+PASS)
Cumulative | 1 | 2 | 3
| Wiggles |  |  | Fraction
Date (yymmdd) | in negative(-) threshold | in both +,-thresholds | containing >0.45 fC | in negative(-) or both (+,-) threshold | in both +,-thresholds | containing >0.45 fC
030501 | 6 | 0 | 0 | 8.333% | 0% | 0%
030601 | 8 | 0 | 0 | 8.163% | 0% | 0%
030701 | 8 | 0 | 0 | 7.207% | 0% | 0%
030801 | 8 | 0 | 0 | 7.207% | 0% | 0%
030901 | 8 | 0 | 0 | 6.557% | 0% | 0%
031001 | 8 | 0 | 0 | 6.015% | 0% | 0%
031101 | 12 | 0 | 0 | 6.667% | 0% | 0%
031201 | 13 | 0 | 0 | 6.533% | 0% | 0%
040101 | 13 | 0 | 0 | 6.22% | 0% | 0%
040201 | 16 | 0 | 0 | 6.987% | 0% | 0%
040301 | 16 | 0 | 0 | 5.714% | 0% | 0%
040401 | 22 | 0 | 0 | 6.647% | 0% | 0%
040501 | 34 | 0 | 0 | 9.214% | 0% | 0%
040601 | 43 | 0 | 0 | 10.54% | 0% | 0%
040701 | 53 | 2 | 1 | 12.14% | 0.4415% | 0.2208%
040801 | 59 | 3 | 1 | 12.86% | 0.6224% | 0.2075%
040901 | 62 | 5 | 1 | 12.71% | 0.9488% | 0.1898%
041001 | 69 | 5 | 1 | 12.85% | 0.8681% | 0.1736%
041101 | 78 | 5 | 1 | 14.02% | 0.8446% | 0.1689%
041201 | 81 | 5 | 1 | 14.53% | 0.8446% | 0.1689%
050101 | 81 | 5 | 1 | 14.53% | 0.8446% | 0.1689%
050201 | 81 | 5 | 1 | 14.53% | 0.8446% | 0.1689%

## ASICstuffing
Cluster | UKB
ASIC stuffing (hybrid counts)
| 1 | 2 | 3 | 4 | 5.1 | 5.2
Cumulative | GOOD | REPAIRED | HOLD | FAIL | STARTED |  | YIELD
Date (yymmdd) | ready for hybrid mounting | e.g GOOD after ASIC replacement | e.g., with defective ASIC's | damaged, no recovery | ASIC stuffing | ASIC-hybrids Classified | (GOOD+REPAIRED)/SUM(1to4) | anticipated
030501 | 5.2: 0 | #DIV/0! | #DIV/0!
030601 | 5.2: 0 | #DIV/0! | #DIV/0!
030701 | 151 | 5 | 22 | 3 | 181 | 178 | 86.19% | 98.14%
030801 | 158 | 5 | 21 | 3 | 187 | 184 | 87.17% | 98.22%
030901 | 174 | 5 | 22 | 3 | 220 | 201 | 87.75% | 98.37%
031001 | 204 | 9 | 22 | 3 | 248 | 235 | 89.5% | 98.62%
031101 | 217 | 13 | 15 | 3 | 253 | 245 | 92.74% | 98.72%
031201 | 220 | 19 | 10 | 3 | 254 | 249 | 94.84% | 98.76%
040101 | 220 | 21 | 7 | 3 | 266 | 248 | 96.02% | 98.77%
040201 | 265 | 21 | 11 | 3 | 332 | 297 | 95.33% | 98.96%
040301 | 337 | 21 | 23 | 3 | 419 | 381 | 93.23% | 99.17%
040401 | 372 | 29 | 12 | 3 | 440 | 413 | 96.39% | 99.26%
040501 | 415 | 29 | 16 | 3 | 500 | 460 | 95.9% | 99.33%
040601 | 462 | 30 | 35 | 3 | 567 | 527 | 92.83% | 99.4%
040701 | 544 | 30 | 39 | 3 | 658 | 613 | 93.18% | 99.48%
040801 | 596 | 50 | 27 | 3 | 706 | 673 | 95.56% | 99.54%
040901 | 633 | 51 | 13 | 3 | 730 | 697 | 97.71% | 99.56%
041001 | 649 | 64 | 12 | 3 | 730 | 725 | 97.94% | 99.58%
041101 | 650 | 65 | 12 | 3 | 730 | 727 | 97.95% | 99.58%
041201 | 650 | 65 | 12 | 3 | 730 | 727 | 97.95% | 99.58%
050101 | 650 | 65 | 12 | 3 | 730 | 727 | 97.95% | 99.58%
050201 | 650 | 65 | 12 | 3 | 730 | 727 | 97.95% | 99.58%

## ASICdefects
Cluster | UKB
ASIC defect classification (ASIC counts)
Cumulative
Large Gain Spread (LGS)
Date (yymmdd) | Dead | STUCK-CELL | STUCK-CELL >2/link | ISH=30uA Warm | ISH=30uA COLD | ISH=20uA COLD | TrimDAC loading failed | Negative offset | High offset | Low gain (<45 mV/fC) | Abnormal cal line | SAWTOOTH s-curve | BLG=BHN=BPB (SDF=default) | BLG=BHN=BPB (SDF=0.4) | Others | defective ASIC's
030501 | [15 empty] | 0
030601 | [15 empty] | 0
030701 | 0 | 2 | 0 | 3 | 2 | 1 | 0 | 1 | 0 | 3 | 0 | 4 |  | 0 | 4 | 13
030801 | 0 | 2 | 0 | 3 | 2 | 1 | 0 | 1 | 0 | 3 | 0 | 4 |  | 0 | 4 | 13
030901 | 0 | 4 | 0 | 3 | 2 | 1 | 0 | 1 | 0 | 4 | 0 | 4 |  | 0 | 5 | 15
031001 | 1 | 4 | 0 | 1 | 2 | 3 | 0 | 1 | 0 | 4 | 1 | 6 |  | 0 | 7 | 23
031101 | 0 | 4 | 0 | 2 | 2 | 4 | 0 | 1 | 0 | 4 | 1 | 7 |  | 0 | 7 | 24
031201 | 0 | 4 | 0 | 2 | 2 | 4 | 0 | 1 | 0 | 4 | 1 | 7 |  | 0 | 7 | 24
040101 | 0 | 4 | 0 | 2 | 2 | 4 | 0 | 1 | 0 | 4 | 1 | 7 |  | 0 | 7 | 24
040201 | 0 | 4 | 0 | 3 | 8 | 4 | 0 | 2 | 0 | 4 | 2 | 7 |  | 0 | 8 | 27
040301 | 0 | 4 | 0 | 5 | 12 | 4 | 0 | 4 | 0 | 4 | 5 | 8 |  | 1 | 9 | 35
040401 | 0 | 4 | 0 | 5 | 16 | 4 | 0 | 4 | 0 | 4 | 6 | 8 |  | 1 | 9 | 36
040501 | 0 | 4 | 0 | 6 | 27 | 4 | 1 | 4 | 0 | 4 | 6 | 8 |  | 1 | 10 | 38
040601 | 0 | 4 | 0 | 6 | 30 | 5 | 2 | 4 | 0 | 5 | 12 | 10 |  | 2 | 10 | 50
040701 | 2 | 4 | 0 | 6 | 30 | 5 | 3 | 4 | 0 | 5 | 13 | 11 |  | 3 | 11 | 57
040801 | 4 | 4 | 0 | 12 | 40 | 5 | 3 | 8 | 0 | 5 | 16 | 11 |  | 3 | 13 | 68
040901 | 4 | 4 | 0 | 12 | 40 | 5 | 3 | 9 | 0 | 7 | 18 | 12 |  | 4 | 15 | 77
041001 | 4 | 4 | 0 | 14 | 42 | 5 | 3 | 9 | 1 | 7 | 18 | 13 |  | 4 | 14 | 78
041101 | 4 | 4 | 0 | 14 | 42 | 5 | 3 | 9 | 1 | 7 | 18 | 13 |  | 4 | 14 | 78
041201 | 4 | 4 | 0 | 14 | 42 | 5 | 3 | 9 | 1 | 7 | 18 | 13 |  | 4 | 14 | 78
050101 | 4 | 4 | 0 | 14 | 42 | 5 | 3 | 9 | 1 | 7 | 18 | 13 |  | 4 | 14 | 78
050201 | 4 | 4 | 0 | 14 | 42 | 5 | 3 | 9 | 1 | 7 | 18 | 13 |  | 4 | 14 | 78
Note:
| BLG | Block of Low Gain
| BHN | Block of High Noise
| BPB | Block of "part-bonded" (in hybrids)

## ASICyield
Cluster | UKB
ASIC loss yield
Cumulative
Date (yymmdd) | defective ASIC's | lost in FAILed hybrids | Visual rejects | lost in handling | lost | Loss Yield
030501 | 0 | 0 |  |  | 0 | #DIV/0!
030601 | 0 | 0 |  |  | 0 | #DIV/0!
030701 | 13 | 36 | 3 | 4 | 56 | 2.622%
030801 | 13 | 36 | 3 | 4 | 56 | 2.536%
030901 | 15 | 36 | 5 | 5 | 61 | 2.529%
031001 | 23 | 36 | 5 | 5 | 69 | 2.447%
031101 | 24 | 36 | 5 | 5 | 70 | 2.381%
031201 | 24 | 36 | 5 | 7 | 72 | 2.41%
040101 | 24 | 36 | 5 | 7 | 72 | 2.419%
040201 | 27 | 36 | 8 | 7 | 78 | 2.189%
040301 | 35 | 36 | 8 | 8 | 87 | 1.903%
040401 | 36 | 36 | 8 | 9 | 89 | 1.796%
040501 | 38 | 36 | 9 | 11 | 94 | 1.703%
040601 | 50 | 36 | 14 | 12 | 112 | 1.771%
040701 | 57 | 36 | 21 | 13 | 127 | 1.726%
040801 | 68 | 36 | 44 | 13 | 161 | 1.994%
040901 | 77 | 36 | 54 | 13 | 180 | 2.152%
041001 | 78 | 36 | 54 | 13 | 181 | 2.08%
041101 | 78 | 36 | 54 | 13 | 181 | 2.075%
041201 | 78 | 36 | 54 | 13 | 181 | 2.075%
050101 | 78 | 36 | 54 | 13 | 181 | 2.075%
050201 | 78 | 36 | 54 | 13 | 181 | 2.075%

## Inventory
Cluster | UKB
Inventory
Cumulative | Received: |  |  |  |  | Used (=started (upto FAIL's)): |  |  |  |  | Lost, damaged, in handling and assembly (not counted as started) |  |  |  |  | Stock:
Date (yymmdd) | Sensors | Base-boards | ASIC's | PC-hybrids | ASIC-hybrids | Sensors | Base-boards | ASIC's | PC-hybrids | ASIC-hybrids | Sensors | Base-boards | ASIC's | PC-hybrids | ASIC-hybrids | Sensors | Base-boards | ASIC's | PC-hybrids | ASIC-hybrids
030501 | 2712 | 421 |  |  |  | 528 | 132 | 0 | 0 | [6 empty] | 2184 | 289 | 0 | 0 | 0
030601 | 2712 | 481 |  |  |  | 720 | 180 | 0 | 0 | [6 empty] | 1992 | 301 | 0 | 0 | 0
030701 | 2712 | 481 | 2869 | 190 | 9 | 912 | 228 | 2172 | 181 |  | 6 | 0 |  |  |  | 1794 | 253 | 697 | 9 | 9
030801 | 2712 | 545 | 2761 | 202 | 9 | 1100 | 275 | 2244 | 187 |  | 8 | 0 |  |  |  | 1604 | 270 | 517 | 15 | 9
030901 | 2712 | 589 | 3372 | 234 | 9 | 1148 | 287 | 2640 | 220 |  | 8 | 0 |  |  |  | 1556 | 302 | 732 | 14 | 9
031001 | 2712 | 630 | 4987 | 306 | 19 | 1380 | 345 | 2976 | 248 |  | 8 | 0 |  |  |  | 1324 | 285 | 2011 | 58 | 19
031101 | 2712 | 630 | 4987 | 338 | 19 | 1600 | 400 | 3036 | 253 |  | 8 | 0 |  |  |  | 1104 | 230 | 1951 | 85 | 19
031201 | 2712 | 630 | 4987 | 306 | 19 | 1760 | 440 | 3048 | 254 |  | 8 | 0 |  |  |  | 944 | 190 | 1939 | 52 | 19
040101 | 2712 | 680 | 4987 | 346 | 19 | 1764 | 441 | 3192 | 266 |  | 8 | 0 |  |  |  | 940 | 239 | 1795 | 80 | 19
040201 | 2712 | 680 | 5116 | 400 | 19 | 1964 | 491 | 3984 | 332 |  | 8 | 0 |  |  |  | 740 | 189 | 1132 | 68 | 19
040301 | 2712 | 680 | 5936 | 454 | 19 | 2144 | 536 | 5028 | 419 |  | 8 | 0 |  |  |  | 560 | 144 | 908 | 35 | 19
040401 | 2712 | 722 | 7123 | 493 | 19 | 2348 | 587 | 5280 | 440 |  | 8 | 0 |  |  |  | 356 | 135 | 1843 | 53 | 19
040501 | 2762 | 722 | 7221 | 589 | 19 | 2528 | 632 | 6000 | 500 |  | 8 | 0 |  |  |  | 226 | 90 | 1221 | 89 | 19
040601 | 2883 | 722 | 7986 | 621 | 19 | 2696 | 674 | 6804 | 567 | 19 | 11 | 0 | 112 | 20 |  | 176 | 48 | 1070 | 34 | 0 | Started filling new non-empty columns: some "lost" PC-hybrids may be declared OK
040701 | 2883 | 722 | 11737 | 730 | 19 | 2832 | 708 | 7896 | 658 | 19 | 11 | 0 | 127 | 19 |  | 40 | 14 | 3714 | 53 | 0 | Total ASICs delivered includes many AD1 & worse chips
040801 | 2883 | 722 | 13961 | 770 | 19 | 2832 | 708 | 8472 | 706 | 19 | 11 | 0 | 161 | 20 |  | 40 | 14 | 5328 | 44 | 0
040901 | 2883 | 722 | 13961 | 770 | 19 | 2832 | 708 | 8760 | 730 | 19 | 11 | 0 | 180 | 20 |  | 40 | 14 | 5021 | 20 | 0
041001 | 2864 | 722 | 13961 | 770 | 19 | 2832 | 708 | 8760 | 730 | 19 | 11 | 0 | 181 | 20 |  | 21 | 14 | 5020 | 20 | 0
041101 | 2864 | 722 | 13961 | 770 | 19 | 2832 | 708 | 8760 | 730 | 19 | 11 | 0 | 181 | 20 |  | 21 | 14 | 5020 | 20 | 0
041201 | 2864 | 722 | 13961 | 770 | 19 | 2832 | 708 | 8760 | 730 | 19 | 11 | 0 | 181 | 20 |  | 21 | 14 | 5020 | 20 | 0
050101 | 2864 | 722 | 13961 | 770 | 19 | 2832 | 708 | 8760 | 730 | 19 | 11 | 0 | 181 | 20 |  | 21 | 14 | 5020 | 20 | 0
050201 | 2864 | 722 | 13961 | 770 | 19 | 2832 | 708 | 8760 | 730 | 19 | 11 | 0 | 181 | 20 |  | 21 | 14 | 5020 | 20 | 0

## Location
Cluster | UKB
Module location | outside of assembly location, e.g., irradiation, beamtest, macro assembly site
Module inst. id | 2022033 | 2022017(Japan), 2022038(Nordic), 2022004(US), 2022033(UK) |  | Quality | [6 empty] | Sign-off
Module id | Categories (1.1~5) | Module location/usage | Date (dd/mm/yyyy) | I-V GOOD /PASS2 /SPARE /FAIL | I-V Comment | Electrical GOOD /PASS2 /SPARE /FAIL | Electrical Special Setting (ISH=20,SDF=0.4) | Electrical Comment | S-curves Category ((ok or good) /negative /positive />0.45) | S-curves Comment | Category GOOD /PASS /PASS2 /SPARE /FAIL | Reason for FAIL | Barrel assignment Any/B5B6/B6 | Reason for B5B6 or B6 | Sign-off Comment
20220330200001
20220330200002
20220330200003
20220330200004
20220330200005
20220330200006
20220330200007
20220330200008
20220330200009
20220330200010
20220330200011
20220330200012
20220330200013
20220330200014
20220330200015
20220330200016
20220330200017
20220330200018
20220330200019
20220330200020
20220330200021
20220330200022
20220330200023
20220330200024
20220330200025
20220330200026
20220330200027
20220330200028
20220330200029
20220330200030
20220330200031
20220330200032
20220330200033
20220330200034
20220330200035
20220330200036
20220330200037
20220330200038
20220330200039
20220330200040
20220330200041
20220330200042
20220330200043
20220330200044
20220330200045
20220330200046
20220330200047
20220330200048
20220330200049
20220330200050
20220330200051
20220330200052
20220330200053
20220330200054
20220330200055
20220330200056
20220330200057
20220330200058
20220330200059
20220330200060
20220330200061
20220330200062
20220330200063
20220330200064
20220330200065
20220330200066
20220330200067
20220330200068
20220330200069
20220330200070
20220330200071
20220330200072
20220330200073
20220330200074
20220330200075
20220330200076
20220330200077
20220330200078
20220330200079
20220330200080
20220330200081
20220330200082
20220330200083
20220330200084
20220330200085
20220330200086
20220330200087
20220330200088
20220330200089
20220330200090
20220330200091
20220330200092
20220330200093
20220330200094
20220330200095
20220330200096
20220330200097
20220330200098
20220330200099
20220330200100
20220330200101
20220330200102
20220330200103
20220330200104
20220330200105
20220330200106
20220330200107
20220330200108
20220330200109
20220330200110
20220330200111
20220330200112
20220330200113
20220330200114
20220330200115
20220330200116
20220330200117
20220330200118
20220330200119
20220330200120
20220330200121
20220330200122
20220330200123
20220330200124
20220330200125
20220330200126
20220330200127
20220330200128
20220330200129
20220330200130
20220330200131
20220330200132
20220330200133
20220330200134
20220330200135
20220330200136
20220330200137
20220330200138
20220330200139
20220330200140
20220330200141
20220330200142
20220330200143
20220330200144
20220330200145
20220330200146
20220330200147
20220330200148
20220330200149
20220330200150
20220330200151
20220330200152
20220330200153
20220330200154
20220330200155
20220330200156
20220330200157
20220330200158
20220330200159
20220330200160
20220330200161
20220330200162
20220330200163
20220330200164
20220330200165
20220330200166
20220330200167
20220330200168
20220330200169
20220330200170
20220330200171
20220330200172
20220330200173
20220330200174
20220330200175
20220330200176
20220330200177
20220330200178
20220330200179
20220330200180
20220330200181
20220330200182
20220330200183
20220330200184
20220330200185
20220330200186
20220330200187
20220330200188
20220330200189
20220330200190
20220330200191
20220330200192
20220330200193
20220330200194
20220330200195
20220330200196
20220330200197
20220330200198
20220330200199
20220330200200
20220330200201
20220330200202
20220330200203
20220330200204
20220330200205
20220330200206
20220330200207
20220330200208
20220330200209
20220330200210
20220330200211
20220330200212
20220330200213
20220330200214
20220330200215
20220330200216
20220330200217
20220330200218
20220330200219
20220330200220
20220330200221
20220330200222
20220330200223
20220330200224
20220330200225
20220330200226
20220330200227
20220330200228
20220330200229
20220330200230
20220330200231
20220330200232
20220330200233
20220330200234
20220330200235
20220330200236
20220330200237
20220330200238
20220330200239
20220330200240
20220330200241
20220330200242
20220330200243
20220330200244
20220330200245
20220330200246
20220330200247
20220330200248
20220330200249
20220330200250
20220330200251
20220330200252
20220330200253
20220330200254
20220330200255
20220330200256
20220330200257
20220330200258
20220330200259
20220330200260
20220330200261
20220330200262
20220330200263
20220330200264
20220330200265
20220330200266
20220330200267
20220330200268
20220330200269
20220330200270
20220330200271
20220330200272
20220330200273
20220330200274
20220330200275
20220330200276
20220330200277
20220330200278
20220330200279
20220330200280
20220330200281
20220330200282
20220330200283
20220330200284
20220330200285
20220330200286
20220330200287
20220330200288
20220330200289
20220330200290
20220330200291
20220330200292
20220330200293
20220330200294
20220330200295
20220330200296
20220330200297
20220330200298
20220330200299
20220330200300
20220330200301
20220330200302
20220330200303
20220330200304
20220330200305
20220330200306
20220330200307
20220330200308
20220330200309
20220330200310
20220330200311
20220330200312
20220330200313
20220330200314
20220330200315
20220330200316
20220330200317
20220330200318
20220330200319
20220330200320
20220330200321
20220330200322
20220330200323
20220330200324
20220330200325
20220330200326
20220330200327
20220330200328
20220330200329
20220330200330
20220330200331
20220330200332
20220330200333
20220330200334
20220330200335
20220330200336
20220330200337
20220330200338
20220330200339
20220330200340
20220330200341
20220330200342
20220330200343
20220330200344
20220330200345
20220330200346
20220330200347
20220330200348
20220330200349
20220330200350
20220330200351
20220330200352
20220330200353
20220330200354
20220330200355
20220330200356
20220330200357
20220330200358
20220330200359
20220330200360
20220330200361
20220330200362
20220330200363
20220330200364
20220330200365
20220330200366
20220330200367
20220330200368
20220330200369
20220330200370
20220330200371
20220330200372
20220330200373
20220330200374
20220330200375
20220330200376
20220330200377
20220330200378
20220330200379
20220330200380
20220330200381
20220330200382
20220330200383
20220330200384
20220330200385
20220330200386
20220330200387
20220330200388
20220330200389
20220330200390
20220330200391
20220330200392
20220330200393
20220330200394
20220330200395
20220330200396
20220330200397
20220330200398
20220330200399
20220330200400
20220330200401
20220330200402
20220330200403
20220330200404
20220330200405
20220330200406
20220330200407
20220330200408
20220330200409
20220330200410
20220330200411
20220330200412
20220330200413
20220330200414
20220330200415
20220330200416
20220330200417
20220330200418
20220330200419
20220330200420
20220330200421
20220330200422
20220330200423
20220330200424
20220330200425
20220330200426
20220330200427
20220330200428
20220330200429
20220330200430
20220330200431
20220330200432
20220330200433
20220330200434
20220330200435
20220330200436
20220330200437
20220330200438
20220330200439
20220330200440
20220330200441
20220330200442
20220330200443
20220330200444
20220330200445
20220330200446
20220330200447
20220330200448
20220330200449
20220330200450
20220330200451
20220330200452
20220330200453
20220330200454
20220330200455
20220330200456
20220330200457
20220330200458
20220330200459
20220330200460
20220330200461
20220330200462
20220330200463
20220330200464
20220330200465
20220330200466
20220330200467
20220330200468
20220330200469
20220330200470
20220330200471
20220330200472
20220330200473
20220330200474
20220330200475
20220330200476
20220330200477
20220330200478
20220330200479
20220330200480
20220330200481
20220330200482
20220330200483
20220330200484
20220330200485
20220330200486
20220330200487
20220330200488
20220330200489
20220330200490
20220330200491
20220330200492
20220330200493
20220330200494
20220330200495
20220330200496
20220330200497
20220330200498
20220330200499
20220330200500
20220330200501
20220330200502
20220330200503
20220330200504
20220330200505
20220330200506
20220330200507
20220330200508
20220330200509
20220330200510
20220330200511
20220330200512
20220330200513
20220330200514
20220330200515
20220330200516
20220330200517
20220330200518
20220330200519
20220330200520
20220330200521
20220330200522
20220330200523
20220330200524
20220330200525
20220330200526
20220330200527
20220330200528
20220330200529
20220330200530
20220330200531
20220330200532
20220330200533
20220330200534
20220330200535
20220330200536
20220330200537
20220330200538
20220330200539
20220330200540
20220330200541
20220330200542
20220330200543
20220330200544
20220330200545
20220330200546
20220330200547
20220330200548
20220330200549
20220330200550
20220330200551
20220330200552
20220330200553
20220330200554
20220330200555
20220330200556
20220330200557
20220330200558
20220330200559
20220330200560
20220330200561
20220330200562
20220330200563
20220330200564
20220330200565
20220330200566
20220330200567
20220330200568
20220330200569
20220330200570
20220330200571
20220330200572
20220330200573
20220330200574
20220330200575
20220330200576
20220330200577
20220330200578
20220330200579
20220330200580
20220330200581
20220330200582
20220330200583
20220330200584
20220330200585
20220330200586
20220330200587
20220330200588
20220330200589
20220330200590
20220330200591
20220330200592
20220330200593
20220330200594
20220330200595
20220330200596
20220330200597
20220330200598
20220330200599
20220330200600
20220330200601
20220330200602
20220330200603
20220330200604
20220330200605
20220330200606
20220330200607
20220330200608
20220330200609
20220330200610
20220330200611
20220330200612
20220330200613
20220330200614
20220330200615
20220330200616
20220330200617
20220330200618
20220330200619
20220330200620
20220330200621
20220330200622
20220330200623
20220330200624
20220330200625
20220330200626
20220330200627
20220330200628
20220330200629
20220330200630
20220330200631
20220330200632
20220330200633
20220330200634
20220330200635
20220330200636
20220330200637
20220330200638
20220330200639
20220330200640
20220330200641
20220330200642
20220330200643
20220330200644
20220330200645
20220330200646
20220330200647
20220330200648
20220330200649
20220330200650
20220330200651
20220330200652
20220330200653
20220330200654
20220330200655
20220330200656
20220330200657
20220330200658
20220330200659
20220330200660
20220330200661
20220330200662
20220330200663
20220330200664
20220330200665
20220330200666
20220330200667
20220330200668
20220330200669
20220330200670
20220330200671
20220330200672
20220330200673
20220330200674
20220330200675
20220330200676
20220330200677
20220330200678
20220330200679
20220330200680
20220330200681
20220330200682
20220330200683
20220330200684
20220330200685
20220330200686
20220330200687
20220330200688
20220330200689
20220330200690
20220330200691
20220330200692
20220330200693
20220330200694
20220330200695
20220330200696
20220330200697
20220330200698
20220330200699
20220330200700
20220330200701
20220330200702
20220330200703
20220330200704
20220330200705
20220330200706
20220330200707
20220330200708
20220330200709
20220330200710
20220330200711
20220330200712
20220330200713
20220330200714
20220330200715
20220330200716
20220330200717
20220330200718
20220330200719
20220330200720
20220330200721
20220330200722
20220330200723
20220330200724
20220330200725
20220330200726
20220330200727
20220330200728
20220330200729
20220330200730
20220330200731
20220330200732
20220330200733
20220330200734
20220330200735
20220330200736
20220330200737
20220330200738
20220330200739
20220330200740
20220330200741
20220330200742
20220330200743
20220330200744
20220330200745
20220330200746
20220330200747
20220330200748
20220330200749
20220330200750
20220330200751
20220330200752
20220330200753
20220330200754
20220330200755
20220330200756
20220330200757
20220330200758
20220330200759
20220330200760
20220330200761
20220330200762
20220330200763
20220330200764
20220330200765
20220330200766
20220330200767
20220330200768
20220330200769
20220330200770
20220330200771
20220330200772
20220330200773
20220330200774
20220330200775
20220330200776
20220330200777
20220330200778
20220330200779
20220330200780
20220330200781
20220330200782
20220330200783
20220330200784
20220330200785
20220330200786
20220330200787
20220330200788
20220330200789
20220330200790
20220330200791
20220330200792
20220330200793
20220330200794
20220330200795
20220330200796
20220330200797
20220330200798
20220330200799
20220330200800
20220330200801
20220330200802
20220330200803
20220330200804
20220330200805
20220330200806
20220330200807
20220330200808
20220330200809
20220330200810
20220330200811
20220330200812
20220330200813
20220330200814
20220330200815
20220330200816
20220330200817
20220330200818
20220330200819
20220330200820
20220330200821
20220330200822
20220330200823
20220330200824
20220330200825
20220330200826
20220330200827
20220330200828
20220330200829
20220330200830
20220330200831
20220330200832
20220330200833
20220330200834
20220330200835
20220330200836
20220330200837
20220330200838
20220330200839
20220330200840
20220330200841
20220330200842
20220330200843
20220330200844
20220330200845
20220330200846
20220330200847
20220330200848
20220330200849
20220330200850
20220330200851
20220330200852
20220330200853
20220330200854
20220330200855
20220330200856
20220330200857
20220330200858
20220330200859
20220330200860
20220330200861
20220330200862
20220330200863
20220330200864
20220330200865
20220330200866
20220330200867
20220330200868
20220330200869
20220330200870
20220330200871
20220330200872
20220330200873
20220330200874
20220330200875
20220330200876
20220330200877
20220330200878
20220330200879
20220330200880
20220330200881
20220330200882
20220330200883
20220330200884
20220330200885
20220330200886
20220330200887
20220330200888
20220330200889
20220330200890
20220330200891
20220330200892
20220330200893
20220330200894
20220330200895
20220330200896
20220330200897
20220330200898
20220330200899
20220330200900
20220330200901
20220330200902
20220330200903
20220330200904
20220330200905
20220330200906
20220330200907
20220330200908
20220330200909
20220330200910
20220330200911
20220330200912
20220330200913
20220330200914
20220330200915
20220330200916
20220330200917
20220330200918
20220330200919
20220330200920
20220330200921
20220330200922
20220330200923
20220330200924
20220330200925
20220330200926
20220330200927
20220330200928
20220330200929
20220330200930
20220330200931
20220330200932
20220330200933
20220330200934
20220330200935
20220330200936
20220330200937
20220330200938
20220330200939
20220330200940
20220330200941
20220330200942
20220330200943
20220330200944
20220330200945
20220330200946
20220330200947
20220330200948
20220330200949
20220330200950
20220330200951
20220330200952
20220330200953
20220330200954
20220330200955
20220330200956
20220330200957
20220330200958
20220330200959
20220330200960
20220330200961
20220330200962
20220330200963
20220330200964
20220330200965
20220330200966
20220330200967
20220330200968
20220330200969
20220330200970
20220330200971
20220330200972
20220330200973
20220330200974
20220330200975
20220330200976
20220330200977
20220330200978
20220330200979
20220330200980