BARREL BASEBOARDS

March 2003

- Component Status

1.1	BeO

- Total Delivery completed in February 2003

1.2	TPG

- Total delivery completed in December 2002

- Laser cutting of all TPG for Baseboards in standard (sorted) orientation completed end 2002

- Update of Sampling Thermal Conductivity Measurements of Completed Baseboards (Graham Beck):

- Baseboard Statistics

- 2444 Series Baseboards have so far been started in the extended production pipeline

- Despatch Statistics to-date for Series Baseboards:

| KEK (Type 1) | UK (Type 2) | US (Type 2) | Scand (Type 1) |
| --- | --- | --- | --- |
| 569 (81%) | 361 (57%) | 173 (23%) | 100 (22%) |

Total despatched = 1327 (47.5% of maximum final number)

- March delivery for Scand and April for KEK will contain Type 2 BBs

- Please inform us without delay if any problem is seen with a delivered baseboard

- Summary

- We are keeping up with the production and delivery totals we planned in June 2002 (which is a lot of hard work)

- We expect to close the BB production line in October 2003

- After that, no additional BBs can be made – ie the supply is strictly to the planning totals