## lossEnds (2)
Model of module production (1/12/2003) | Japan | UK | US | Scand | Total | 2530 |  | 2530
2500
Target number of modules to ship | 786 | 549 | 483 | 404 | 2222
Number of modules built & classified today | 515 | 245 | 237 | 75 | 1072
Number of 'good+pass' modules for any barrel | 433 |  |  |  | 433 | 19.49%
Number of 'good+pass' modules for B5/B6 | 42 |  |  |  | 42 | 1.89%
Number of 'good+pass' modules | 475 | 204 | 175 | 67 | 921
Fraction of modules completed (%) | 60.43% | 37.16% | 36.23% | 16.58% |  | 41.45%
Number of modules missing today | 311 | 345 | 308 | 337 | 1301 | 58.55%
Yield & Inventory |  | 0.83265 |  | 0.89333
% yield achieved so far | 92.23% | 85% | 73.84% | 85% | 85.91%
Maximum No. of sets of parts available to cluster | 894.9505 | 625.099 | 549.9505 | 460 | 2530 |  |  | 10120
Number of "good+pass" modules expected | 825.4398 | 531.3342 | 406.0816 | 391 | 2153.8555
Numer of missing modules | -39.4398 | 17.6658 | 76.9184 | 13 | 68.1445 | 2609.3169
Outlook
Acquire missing sets to start and to the most successful | 73.883 | 0 | [5 empty] | 295.5318 | 10415.5318
Remaining number of modules required to complete | 418.5843 | 327.3342 | 231.0816 | 324 | 1301
Predicted module start average rate/day | 3 | 2.8 | 2.5 | 1.6 | 9.9
Predicted 'good+pass' module average rate | 2.767 | 2.38 | 1.846 | 1.36 | 8.353
Estimated time to qualify (weeks) | 4 | 0 | 0 | 0
Calculated time to completion(weeks) | 34.2556 | 27.5071 | 25.036 | 47.6471 | 47.6471
Revise sharing of remaining modules to minimise time
Estimated number of modules in 4 weeks | 0 | 47.6 | 36.9198 | 27.2
Estimated number of modules missing in 4 weeks | 418.5843 | 279.7342 | 194.1618 | 296.8 | 1189.2802
Revised sharing of remaining modules to minimise time | 423.1577 | 363.975 | 194.1618 | 207.9857 | 1189.2802
Revised sharing converted into number of new starts | 458.792 | 428.2059 | 262.9505 | 244.6891 | 1394.6375 |  | Completion date
Time to complete(weeks after 1/12/03+4weeks i.e after 1/1/04) | 30.5861 | 30.5861 | 21.036 | 30.5861 |  |  | 2004-09-01 | 7.6465
Revised total number of modules shipped | 898.1577 | 615.575 | 406.0816 | 302.1857 | 2222
Change over initial target | 114.3% | 112.1% | 84.07% | 74.8% |  |  | Number of detectors required
Revised total number of modules to start | 973.792 | 724.2059 | 549.9505 | 355.5126 | 2603.461 |  | 10413.844
Revised total number of modules to start (rounded) | 980 | 720 | 550 | 350 | 2600 |  | 10400
Delta over the line 13 | 85.0495 | 94.901 | 0.049505 | -110