## Introduction
Barrel Modules Status
Version history
1st version | 2003-07-03
1.1 | 2003-07-24
1.2 | 2003-07-29 | updates in Inventory, Pipeline, forB5B6, HOLD, REWORK, s-curves sheets
1.3 | 2003-07-31 | update in Pipeline sheet, add FAIL sheet
1.4 | 2003-08-01 | update in Pipeline, Inventry sheet
1.5 | 2003-08-01 | update in Pipeline (wording, and formula in column I), HOLD (split SB and Module), FAIL, ASICstuffing sheets
1.6 | 2003-08-19 | update in Scurves (wording, >0.4fC), ASICstuffing, ASICyield(formula), add Location sheet, print area
1.7 | 2003-08-26 | update in Categories sheet (listing sums of GOOD+PASS for barrels)
1.8 | 2003-11-05 | correction of mistypo in categories definition, module for B3 and B4, temperature... <2 deg.C
1.9 | 2004-01-07 | add columns of STUCKCELL>2/link and BHN (block of high noise = partbonded in hybrid) at SDF=0.4, and modify counting of total , in ASICdefects sheet
2.0 | 2004-01-19 | add Quality and Sign-off columns in "Location" sheet. Sign-off "Category" is either of GOOD/PASS/FAIL.
2.1 | 2004-01-20 | add "Electrical special setting" in Quality columns in "Location" sheet
Barrel Module Categories
"SB" is the sensor-baseboard sandwich WITHOUT hybrid
"Module" is the final object, I.e., SB fitted WITH hybrid
When counted, SB's and Modules are exclusive each other.
Also, the entries in 1.1, 1.2, ..., are exclusive each other.
1 | GOOD
Fully completed and tested module, satisfying all specifications (mechanical and electrical).
For electrical performance, it is expected that the large majority of modules will have considerably less than the 1% bad channels of the specification.
Within Good are the subcategories:
1.1 | Good for any barrel
1.2 | Use only for barrel 5 or 6
(See separate proposal for these subcategories)
2 | PASS
The module just misses satisfying one or more of the mechanical specifications.
The purpose of the category is to keep modules in the tails of the expected mechanical distributions.
The number of Pass modules should therefore be much less than the number of Good modules.
A Pass module must still fully satisfy the electrical specification.
Pass modules are agreed to be usable in ATLAS, without further discussion.
Within Pass are the subcategories:
2.1 | Pass for any barrel
2.2 | Use only for barrel 5 or 6
The limits of quantities as measured for the Pass category: see the attached table
3 | HOLD
These are modules outside one or more of the Pass limits.
They are stopped in production at the point they are found to be outside the limit (ie a hybrid is not fitted if the baseboard-sensor sandwich is outside "pass" metrology values).
They are carefully stored for later assessment by the Barrel Module community.
3.1 | SB's
3.2 | Modules (I.e., SB with hybrid)
(e.g., I>4uA at 500V without Microdischarge(MD), MD<350V, Abnormally long current decay , lost channels>7/side, >15/total, etc)
4 | FAIL
Modules that could never go in ATLAS,
for example broken or badly scratched detectors, gross mechanical errors, many bad channels due to bonding problems, broken ASICs that can't be replaced.
4.1 | SB's
4.2 | Modules (I.e., SB with hybrid)
5 | REWORK modules
Modules held back for rework that might make them usable,
e.g., replacing an ASIC, gluing on a replacement pitch adapter, re-bonding work.
6 | Classified
This "Classified" column is the sum of the above exclusive columns, in order to have the total number of classified SB and modules
First proposals for Modules to Select for Barrels 3 and 4
1 | Series (not pre-series) detectors.
2 | No sign of IV 'microdischarge' up to 500V bias (in nitrogen or dry air atmosphere)
3 | No history of unexplained bad IV behaviour (eg current very big on first test of module)
5 | No bad visual inspection features that could relate to HV robustness
(eg unusual amount of debris/marks near detector edges, messy detector-detector bonding that leaves any bonds flat near detector surface, broken bits of bond wire, etc.)
6 | Thermistor temperatures are as expected for test setup and difference in their temperature is <2 deg C
7 | Cooling facing b-angle within specification (I.e., <3 mrad)
8 | Any conclusions on irradiation hardness that might be established in future
Metrology parameters
(The values are including measurement errors)
|  | Parameters | Good | Pass | Hold
|  | mhx [um] | +/-30 | +/-40 | >+/-40.000
|  | mhy [um] | +/-30 | +/-40 | >+/-40.000
|  | msx [um] | +/-100 | +/-140 | >+/-140.000
|  | msy [um] | +/-30 | +/-40 | >+/-40.000
|  | sepf [um] | +/-10 | +/-20 | >+/-20
|  | sepb [um] | +/-10 | +/-20 | >+/-20
|  | midxf [um] | +/-10 |  | >+/-10
|  | midyf [um] | +/-5 | +/-8 | >+/-8
|  | a1 [mrad] | +/-0.13 |  | >+/-0.13
|  | a2 [mrad] | +/-0.13 |  | >+/-0.13
|  | a3 [mrad] | +/-0.13 |  | >+/-0.13
|  | a4 [mrad] | +/-0.13 |  | >+/-0.13
|  | stereo [mrad] | +/-0.13 |  | >+/-0.13
|  | maxZlower [mm] | -0.2 |  | >-0.2
|  | maxZupper [mm] | 0.2 |  | >0.2
|  | moduleThickness [mm] | +/-0.1 |  | >+/-0.1
|  | optimalMaxZerrorLower [mm] | 0.05 | 0.07 | >0.07
|  | optimalMaxZerrorUpper [mm] | 0.05 | 0.07 | >0.07
|  | optimalRMSZerrorLower [mm] | 0.025 |  | >0.025
|  | optimalRMSZerrorUpper [mm] | 0.025 |  | >0.025
|  | loCoolingFacing a [mrad] | +/-0.5 |  | >+/-0.5
|  | b [mrad] | +/-3 | +/-5 | >+/-5
|  | loCoolingFacingConcavity [mm] | +/-0.03 |  | >+/-0.03
|  | capMaxThickness [mm] | 6.44 |  | >6.44
Pipeline sheet:
1 | SB(Sensor-baseboard) started
2 | SB's sent/ready for classification
3 | SB's classified
4 | SB's sent/ready for hybrid mounting (="SB's classified" - ("SB's HOLD" + "SB's FAIL" in "Categories"))
5 | Modules sent/ready for wire-bonding (I.e., hybrid mounting completed = "SB's ready for hybrid mounting" - "Modules in progress at SB stage on date")
6 | Modules sent/ready for classification (I.e., wire-bonding completed)
7 | Modules classified (= "Classifed" - ("SB's HOLD"+"SB's FAIL") in "Categories")
- | Calculation/given | Modules in progress at SB stage on date(="SB's sent/ready for hybrid mounting" - "Modules sent/ready for wire-bonding")
- | Calculation/given | Modules in progress with hybrid mounted on date(="Modules sent/ready for wire-bonding" - "Modules classified")
HOLD sheet:
1 | SB out of PASS limits
2 | I(500V)>4uA without microdischarge (MD<350) without annealing
3 | MD<350V
4 | Abnormally long current decay at 500V, >1hr
5 | Lost channels >7consective/side, >15/total
6 | Bad s-curves >0.5fC
7 | Others
REWORK sheet:
Modules are requiring further actions:
1 | replacing an ASIC
2 | replacing a pitch adaper
3 | rebonding wires
4 | replacing hybrid
5 | replacing connector
6 | further visual inspection
7 | cleaning
8 | others
Location sheet:
| Module id |  | First 7 digits can be automated with B3 cell
| Categories |  | 1.1~5 | Mandatory to be filled that automatically fills "Category" and "Barrel assignment" cells
Module location/usage
| Date |  | (dd/mm/yyyy) | Date of filling the row
| I-V |  | GOOD/FAIL
| I-V |  | Comment
| Electrical |  | GOOD/FAIL
| Electrical Special Setting |  | ISH=20, SDF=0.4
| Electrical |  | Comment
| S-curves Category |  | (-,+,>0.45) | "-": wiggle in negative threshold, "+": wiggles in both negative and positive threaholds, ">0.45": wiggles threshold > 0.45fC
| S-curves |  | Comment
| Category |  | GOOD/PASS/HOLD/FAIL/REWORK, automatically filled from the "Categories" value
Reason for HOLD/FAIL
| Barrel assignment |  | Any/B5B6, automatically filled from the "Categories" value
Reason for B5B6
Sign-off comment

## Pipeline
Cluster | XXX
Pipeline | ("sent" means either sent or ready to be sent)
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Cumulative
Date (yymmdd) | SB's started | SB's sent/ready for classification | SB's classified | SB's sent/ready for hybrid mounting | Modules sent/ready for wire-bonding | Modules sent/ready for classification | Modules classified | Modules in progress at SB stage on date (=(4)-(5)) | Modules in progress with hybrid mounted on date(=(5)-(7))
030501 | [7 empty] | 0 | 0
030601 | [7 empty] | 0 | 0
030701 | [7 empty] | 0 | 0
030801 | [7 empty] | 0 | 0
030901 | [7 empty] | 0 | 0
031001 | [7 empty] | 0 | 0
031101 | [7 empty] | 0 | 0
031201 | [7 empty] | 0 | 0
040101 | [7 empty] | 0 | 0
040201 | [7 empty] | 0 | 0
040301 | [7 empty] | 0 | 0
040401 | [7 empty] | 0 | 0
040501 | [7 empty] | 0 | 0
040601 | [7 empty] | 0 | 0
040701 | [7 empty] | 0 | 0
040801 | [7 empty] | 0 | 0
040901 | [7 empty] | 0 | 0
041001 | [7 empty] | 0 | 0
041101 | [7 empty] | 0 | 0
041201 | [7 empty] | 0 | 0

## Categories
Cluster | XXX
Module categories (each column entry is exclusive each other)
| 1.1 | 1.2 | 2.1 | 2.2 | 3.1 | 3.2 | 4.1 | 4.2 | 5 | 6
Cumulative | GOOD |  | PASS |  | HOLD |  | FAIL |  | REWORK |  | GOOD+PASS |  |  | YIELD
Date (yymmdd) | for any barrel | for B5/B6 | for any barrel | for B5/B6 | SB's | Modules | SB's | Modules | Modules | Classified | for any barrel | for B5/B6 | total | PASS /(GOOD+PASS) | (GOOD+PASS) /Classified | HOLD /Classified | FAIL /Classified | REWORK /Classified
030501 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
030601 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
030701 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
030801 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
030901 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
031001 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
031101 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
031201 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
040101 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
040201 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
040301 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
040401 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
040501 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
040601 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
040701 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
040801 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
040901 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
041001 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
041101 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
041201 | [9 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## forB5B6
Cluster | XXX
Modules for B5/B6
Reasons:
Cumulative | 1 | 2 | 3 | 5 | 6 | 7 | 8
Date (yymmdd) | Pre-series sensors | MD>350V | Bad current behaviour | Bad visual features | Thermistor T diff.>=2C | b angle >3 mrad | Irradiation aspects
030501
030601
030701
030801
030901
031001
031101
031201
040101
040201
040301
040401
040501
040601
040701
040801
040901
041001
041101
041201

## HOLD
Cluster | XXX
SB or Modules in HOLD
Reasons:
| SB |  | Module
Cumulative | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Date (yymmdd) | Out of PASS limits | Others | Out of PASS limit | I(500V)>4uA W/O MD<350V | MD<350V | Abnormally long current decay, >1hr | Lost ch. >7consective/side, >15/total | Bad s-curves >0.5fC | Others
030501
030601
030701
030801
030901
031001
031101
031201
040101
040201
040301
040401
040501
040601
040701
040801
040901
041001
041101
041201

## FAIL
Cluster | XXX
SB or Modules in FAIL
Reasons:
| SB |  |  |  | Module
Cumulative | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Date (yymmdd) | Sensor damaged | BB damaged | Gross mechanical error | Others | Sensor damaged | BB damaged | Gross mechanical error | Abnormal leakge current | Too many bad channels | ASIC's non-replaceable | Others
030501
030601
030701
030801
030901
031001
031101
031201
040101
040201
040301
040401
040501
040601
040701
040801
040901
041001
041101
041201

## REWORK
Cluster | XXX
Modules in REWORK
Reasons: requiring ...
Cumulative | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Date (yymmdd) | replacing ASIC | replacing PA | rebonding wires | replacing hybrid | replacing connector | further visual inspection | cleaning | others
030501
030601
030701
030801
030901
031001
031101
031201
040101
040201
040301
040401
040501
040601
040701
040801
040901
041001
041101
041201

## Scurves
Cluster | XXX
S-curve wiggles in Noise-Occupancy plots in modules (GOOD+PASS)
Cumulative | 1 | 2 | 3
| Wiggles |  |  | Fraction
Date (yymmdd) | in negative(-) threshold | in both +,-thresholds | containing >0.4 fC | in negative(-) or both (+,-) threshold | in both +,-thresholds | containing >0.4 fC
030501 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
030601 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
030701 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
030801 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
030901 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
031001 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
031101 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
031201 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
040101 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
040201 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
040301 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
040401 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
040501 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
040601 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
040701 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
040801 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
040901 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
041001 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
041101 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
041201 |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!

## ASICstuffing
Cluster | XXX
ASIC stuffing (hybrid counts)
| 1 | 2 | 3 | 4 | 5.1 | 5.2
Cumulative | GOOD | REPAIRED | HOLD | FAIL | STARTED |  | YIELD
Date (yymmdd) | ready for hybrid mounting | e.g GOOD after ASIC replacement | e.g., with defective ASIC's | damaged, no recovery | ASIC stuffing | ASIC-hybrids Classified | (GOOD+REPAIRED)/SUM(1to4) | anticipated
030501 | 5.2: 0 | #DIV/0! | #DIV/0!
030601 | 5.2: 0 | #DIV/0! | #DIV/0!
030701 | 5.2: 0 | #DIV/0! | #DIV/0!
030801 | 5.2: 0 | #DIV/0! | #DIV/0!
030901 | 5.2: 0 | #DIV/0! | #DIV/0!
031001 | 5.2: 0 | #DIV/0! | #DIV/0!
031101 | 5.2: 0 | #DIV/0! | #DIV/0!
031201 | 5.2: 0 | #DIV/0! | #DIV/0!
040101 | 5.2: 0 | #DIV/0! | #DIV/0!
040201 | 5.2: 0 | #DIV/0! | #DIV/0!
040301 | 5.2: 0 | #DIV/0! | #DIV/0!
040401 | 5.2: 0 | #DIV/0! | #DIV/0!
040501 | 5.2: 0 | #DIV/0! | #DIV/0!
040601 | 5.2: 0 | #DIV/0! | #DIV/0!
040701 | 5.2: 0 | #DIV/0! | #DIV/0!
040801 | 5.2: 0 | #DIV/0! | #DIV/0!
040901 | 5.2: 0 | #DIV/0! | #DIV/0!
041001 | 5.2: 0 | #DIV/0! | #DIV/0!
041101 | 5.2: 0 | #DIV/0! | #DIV/0!
041201 | 5.2: 0 | #DIV/0! | #DIV/0!

## ASICdefects
Cluster | XXX
ASIC defect classification (ASIC counts)
Cumulative
Large Gain Spread (LGS)
Date (yymmdd) | Dead | STUCK-CELL | STUCK-CELL >2/link | ISH=30uA Warm | ISH=30uA COLD | ISH=20uA COLD | TrimDAC loading failed | Negative offset | High offset | Low gain (<45 mV/fC) | Abnormal cal line | SAWTOOTH s-curve | BLG=BHN=BPB (SDF=default) | BLG=BHN=BPB (SDF=0.4) | Others | defective ASIC's
030501 | [15 empty] | 0
030601 | [15 empty] | 0
030701 | [15 empty] | 0
030801 | [15 empty] | 0
030901 | [15 empty] | 0
031001 | [15 empty] | 0
031101 | [15 empty] | 0
031201 | [15 empty] | 0
040101 | [15 empty] | 0
040201 | [15 empty] | 0
040301 | [15 empty] | 0
040401 | [15 empty] | 0
040501 | [15 empty] | 0
040601 | [15 empty] | 0
040701 | [15 empty] | 0
040801 | [15 empty] | 0
040901 | [15 empty] | 0
041001 | [15 empty] | 0
041101 | [15 empty] | 0
041201 | [15 empty] | 0
Note:
| BLG | Block of Low Gain
| BHN | Block of High Noise
| BPB | Block of "part-bonded" (in hybrids)

## ASICyield
Cluster | XXX
ASIC loss yield
Cumulative
Date (yymmdd) | defective ASIC's | lost in FAILed hybrids | Visual rejects | lost in handling | lost | Loss Yield
030501 | 0 | 0 |  |  | 0 | #DIV/0!
030601 | 0 | 0 |  |  | 0 | #DIV/0!
030701 | 0 | 0 |  |  | 0 | #DIV/0!
030801 | 0 | 0 |  |  | 0 | #DIV/0!
030901 | 0 | 0 |  |  | 0 | #DIV/0!
031001 | 0 | 0 |  |  | 0 | #DIV/0!
031101 | 0 | 0 |  |  | 0 | #DIV/0!
031201 | 0 | 0 |  |  | 0 | #DIV/0!
040101 | 0 | 0 |  |  | 0 | #DIV/0!
040201 | 0 | 0 |  |  | 0 | #DIV/0!
040301 | 0 | 0 |  |  | 0 | #DIV/0!
040401 | 0 | 0 |  |  | 0 | #DIV/0!
040501 | 0 | 0 |  |  | 0 | #DIV/0!
040601 | 0 | 0 |  |  | 0 | #DIV/0!
040701 | 0 | 0 |  |  | 0 | #DIV/0!
040801 | 0 | 0 |  |  | 0 | #DIV/0!
040901 | 0 | 0 |  |  | 0 | #DIV/0!
041001 | 0 | 0 |  |  | 0 | #DIV/0!
041101 | 0 | 0 |  |  | 0 | #DIV/0!
041201 | 0 | 0 |  |  | 0 | #DIV/0!

## Inventory
Cluster | XXX
Inventory
Cumulative | Received: |  |  |  |  | Used (=started (upto FAIL's)): |  |  |  |  | Lost, damaged, in handling and assembly (not counted as started) |  |  |  |  | Stock:
Date (yymmdd) | Sensors | Base-boards | ASIC's | PC-hybrids | ASIC-hybrids | Sensors | Base-boards | ASIC's | PC-hybrids | ASIC-hybrids | Sensors | Base-boards | ASIC's | PC-hybrids | ASIC-hybrids | Sensors | Base-boards | ASIC's | PC-hybrids | ASIC-hybrids
030501 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
030601 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
030701 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
030801 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
030901 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
031001 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
031101 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
031201 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
040101 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
040201 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
040301 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
040401 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
040501 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
040601 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
040701 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
040801 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
040901 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
041001 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
041101 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
041201 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0

## Location
Cluster | XXX
Module location | outside of assembly location, e.g., irradiation, beamtest, macro assembly site
Module inst. id | 2022017 | 2022017(Japan), 2022038(Nordic), 2022004(US), 2022033(UK) |  | Quality | [6 empty] | Sign-off
Module id | Categories (1.1~5) | Module location/usage | Date (dd/mm/yyyy) | I-V GOOD/FAIL | I-V Comment | Electrical GOOD/FAIL | Electrical Special Setting (ISH=20,SDF=0.4) | Electrical Comment | S-curves Category (-,+,>0.45) | S-curves Comment | Category GOOD/PASS/FAIL | Reason for FAIL | Barrel assignment Any/B5B6 | Reason for B5B6 | Sign-off Comment
20220170200001
20220170200002
20220170200003
20220170200004
20220170200005
20220170200006
20220170200007
20220170200008
20220170200009
20220170200010
20220170200011
20220170200012
20220170200013
20220170200014
20220170200015
20220170200016
20220170200017
20220170200018
20220170200019
20220170200020
20220170200021
20220170200022
20220170200023
20220170200024
20220170200025
20220170200026
20220170200027
20220170200028
20220170200029
20220170200030
20220170200031
20220170200032
20220170200033
20220170200034
20220170200035
20220170200036
20220170200037
20220170200038
20220170200039
20220170200040
20220170200041
20220170200042
20220170200043
20220170200044
20220170200045
20220170200046
20220170200047
20220170200048
20220170200049
20220170200050
20220170200051
20220170200052
20220170200053
20220170200054
20220170200055
20220170200056
20220170200057
20220170200058
20220170200059
20220170200060
20220170200061
20220170200062
20220170200063
20220170200064
20220170200065
20220170200066
20220170200067
20220170200068
20220170200069
20220170200070
20220170200071
20220170200072
20220170200073
20220170200074
20220170200075
20220170200076
20220170200077
20220170200078
20220170200079
20220170200080
20220170200081
20220170200082
20220170200083
20220170200084
20220170200085
20220170200086
20220170200087
20220170200088
20220170200089
20220170200090
20220170200091
20220170200092
20220170200093
20220170200094
20220170200095
20220170200096
20220170200097
20220170200098
20220170200099
20220170200100
20220170200101
20220170200102
20220170200103
20220170200104
20220170200105
20220170200106
20220170200107
20220170200108
20220170200109
20220170200110
20220170200111
20220170200112
20220170200113
20220170200114
20220170200115
20220170200116
20220170200117
20220170200118
20220170200119
20220170200120
20220170200121
20220170200122
20220170200123
20220170200124
20220170200125
20220170200126
20220170200127
20220170200128
20220170200129
20220170200130
20220170200131
20220170200132
20220170200133
20220170200134
20220170200135
20220170200136
20220170200137
20220170200138
20220170200139
20220170200140
20220170200141
20220170200142
20220170200143
20220170200144
20220170200145
20220170200146
20220170200147
20220170200148
20220170200149
20220170200150
20220170200151
20220170200152
20220170200153
20220170200154
20220170200155
20220170200156
20220170200157
20220170200158
20220170200159
20220170200160
20220170200161
20220170200162
20220170200163
20220170200164
20220170200165
20220170200166
20220170200167
20220170200168
20220170200169
20220170200170
20220170200171
20220170200172
20220170200173
20220170200174
20220170200175
20220170200176
20220170200177
20220170200178
20220170200179
20220170200180
20220170200181
20220170200182
20220170200183
20220170200184
20220170200185
20220170200186
20220170200187
20220170200188
20220170200189
20220170200190
20220170200191
20220170200192
20220170200193
20220170200194
20220170200195
20220170200196
20220170200197
20220170200198
20220170200199
20220170200200
20220170200201
20220170200202
20220170200203
20220170200204
20220170200205
20220170200206
20220170200207
20220170200208
20220170200209
20220170200210
20220170200211
20220170200212
20220170200213
20220170200214
20220170200215
20220170200216
20220170200217
20220170200218
20220170200219
20220170200220
20220170200221
20220170200222
20220170200223
20220170200224
20220170200225
20220170200226
20220170200227
20220170200228
20220170200229
20220170200230
20220170200231
20220170200232
20220170200233
20220170200234
20220170200235
20220170200236
20220170200237
20220170200238
20220170200239
20220170200240
20220170200241
20220170200242
20220170200243
20220170200244
20220170200245
20220170200246
20220170200247
20220170200248
20220170200249
20220170200250
20220170200251
20220170200252
20220170200253
20220170200254
20220170200255
20220170200256
20220170200257
20220170200258
20220170200259
20220170200260
20220170200261
20220170200262
20220170200263
20220170200264
20220170200265
20220170200266
20220170200267
20220170200268
20220170200269
20220170200270
20220170200271
20220170200272
20220170200273
20220170200274
20220170200275
20220170200276
20220170200277
20220170200278
20220170200279
20220170200280
20220170200281
20220170200282
20220170200283
20220170200284
20220170200285
20220170200286
20220170200287
20220170200288
20220170200289
20220170200290
20220170200291
20220170200292
20220170200293
20220170200294
20220170200295
20220170200296
20220170200297
20220170200298
20220170200299
20220170200300
20220170200301
20220170200302
20220170200303
20220170200304
20220170200305
20220170200306
20220170200307
20220170200308
20220170200309
20220170200310
20220170200311
20220170200312
20220170200313
20220170200314
20220170200315
20220170200316
20220170200317
20220170200318
20220170200319
20220170200320
20220170200321
20220170200322
20220170200323
20220170200324
20220170200325
20220170200326
20220170200327
20220170200328
20220170200329
20220170200330
20220170200331
20220170200332
20220170200333
20220170200334
20220170200335
20220170200336
20220170200337
20220170200338
20220170200339
20220170200340
20220170200341
20220170200342
20220170200343
20220170200344
20220170200345
20220170200346
20220170200347
20220170200348
20220170200349
20220170200350
20220170200351
20220170200352
20220170200353
20220170200354
20220170200355
20220170200356
20220170200357
20220170200358
20220170200359
20220170200360
20220170200361
20220170200362
20220170200363
20220170200364
20220170200365
20220170200366
20220170200367
20220170200368
20220170200369
20220170200370
20220170200371
20220170200372
20220170200373
20220170200374
20220170200375
20220170200376
20220170200377
20220170200378
20220170200379
20220170200380
20220170200381
20220170200382
20220170200383
20220170200384
20220170200385
20220170200386
20220170200387
20220170200388
20220170200389
20220170200390
20220170200391
20220170200392
20220170200393
20220170200394
20220170200395
20220170200396
20220170200397
20220170200398
20220170200399
20220170200400
20220170200401
20220170200402
20220170200403
20220170200404
20220170200405
20220170200406
20220170200407
20220170200408
20220170200409
20220170200410
20220170200411
20220170200412
20220170200413
20220170200414
20220170200415
20220170200416
20220170200417
20220170200418
20220170200419
20220170200420
20220170200421
20220170200422
20220170200423
20220170200424
20220170200425
20220170200426
20220170200427
20220170200428
20220170200429
20220170200430
20220170200431
20220170200432
20220170200433
20220170200434
20220170200435
20220170200436
20220170200437
20220170200438
20220170200439
20220170200440
20220170200441
20220170200442
20220170200443
20220170200444
20220170200445
20220170200446
20220170200447
20220170200448
20220170200449
20220170200450
20220170200451
20220170200452
20220170200453
20220170200454
20220170200455
20220170200456
20220170200457
20220170200458
20220170200459
20220170200460
20220170200461
20220170200462
20220170200463
20220170200464
20220170200465
20220170200466
20220170200467
20220170200468
20220170200469
20220170200470
20220170200471
20220170200472
20220170200473
20220170200474
20220170200475
20220170200476
20220170200477
20220170200478
20220170200479
20220170200480
20220170200481
20220170200482
20220170200483
20220170200484
20220170200485
20220170200486
20220170200487
20220170200488
20220170200489
20220170200490
20220170200491
20220170200492
20220170200493
20220170200494
20220170200495
20220170200496
20220170200497
20220170200498
20220170200499
20220170200500
20220170200501
20220170200502
20220170200503
20220170200504
20220170200505
20220170200506
20220170200507
20220170200508
20220170200509
20220170200510
20220170200511
20220170200512
20220170200513
20220170200514
20220170200515
20220170200516
20220170200517
20220170200518
20220170200519
20220170200520
20220170200521
20220170200522
20220170200523
20220170200524
20220170200525
20220170200526
20220170200527
20220170200528
20220170200529
20220170200530
20220170200531
20220170200532
20220170200533
20220170200534
20220170200535
20220170200536
20220170200537
20220170200538
20220170200539
20220170200540
20220170200541
20220170200542
20220170200543
20220170200544
20220170200545
20220170200546
20220170200547
20220170200548
20220170200549
20220170200550
20220170200551
20220170200552
20220170200553
20220170200554
20220170200555
20220170200556
20220170200557
20220170200558
20220170200559
20220170200560
20220170200561
20220170200562
20220170200563
20220170200564
20220170200565
20220170200566
20220170200567
20220170200568
20220170200569
20220170200570
20220170200571
20220170200572
20220170200573
20220170200574
20220170200575
20220170200576
20220170200577
20220170200578
20220170200579
20220170200580
20220170200581
20220170200582
20220170200583
20220170200584
20220170200585
20220170200586
20220170200587
20220170200588
20220170200589
20220170200590
20220170200591
20220170200592
20220170200593
20220170200594
20220170200595
20220170200596
20220170200597
20220170200598
20220170200599
20220170200600
20220170200601
20220170200602
20220170200603
20220170200604
20220170200605
20220170200606
20220170200607
20220170200608
20220170200609
20220170200610
20220170200611
20220170200612
20220170200613
20220170200614
20220170200615
20220170200616
20220170200617
20220170200618
20220170200619
20220170200620
20220170200621
20220170200622
20220170200623
20220170200624
20220170200625
20220170200626
20220170200627
20220170200628
20220170200629
20220170200630
20220170200631
20220170200632
20220170200633
20220170200634
20220170200635
20220170200636
20220170200637
20220170200638
20220170200639
20220170200640
20220170200641
20220170200642
20220170200643
20220170200644
20220170200645
20220170200646
20220170200647
20220170200648
20220170200649
20220170200650
20220170200651
20220170200652
20220170200653
20220170200654
20220170200655
20220170200656
20220170200657
20220170200658
20220170200659
20220170200660
20220170200661
20220170200662
20220170200663
20220170200664
20220170200665
20220170200666
20220170200667
20220170200668
20220170200669
20220170200670
20220170200671
20220170200672
20220170200673
20220170200674
20220170200675
20220170200676
20220170200677
20220170200678
20220170200679
20220170200680
20220170200681
20220170200682
20220170200683
20220170200684
20220170200685
20220170200686
20220170200687
20220170200688
20220170200689
20220170200690
20220170200691
20220170200692
20220170200693
20220170200694
20220170200695
20220170200696
20220170200697
20220170200698
20220170200699
20220170200700
20220170200701
20220170200702
20220170200703
20220170200704
20220170200705
20220170200706
20220170200707
20220170200708
20220170200709
20220170200710
20220170200711
20220170200712
20220170200713
20220170200714
20220170200715
20220170200716
20220170200717
20220170200718
20220170200719
20220170200720
20220170200721
20220170200722
20220170200723
20220170200724
20220170200725
20220170200726
20220170200727
20220170200728
20220170200729
20220170200730
20220170200731
20220170200732
20220170200733
20220170200734
20220170200735
20220170200736
20220170200737
20220170200738
20220170200739
20220170200740
20220170200741
20220170200742
20220170200743
20220170200744
20220170200745
20220170200746
20220170200747
20220170200748
20220170200749
20220170200750
20220170200751
20220170200752
20220170200753
20220170200754
20220170200755
20220170200756
20220170200757
20220170200758
20220170200759
20220170200760
20220170200761
20220170200762
20220170200763
20220170200764
20220170200765
20220170200766
20220170200767
20220170200768
20220170200769
20220170200770
20220170200771
20220170200772
20220170200773
20220170200774
20220170200775
20220170200776
20220170200777
20220170200778
20220170200779
20220170200780
20220170200781
20220170200782
20220170200783
20220170200784
20220170200785
20220170200786
20220170200787
20220170200788
20220170200789
20220170200790
20220170200791
20220170200792
20220170200793
20220170200794
20220170200795
20220170200796
20220170200797
20220170200798
20220170200799
20220170200800
20220170200801
20220170200802
20220170200803
20220170200804
20220170200805
20220170200806
20220170200807
20220170200808
20220170200809
20220170200810
20220170200811
20220170200812
20220170200813
20220170200814
20220170200815
20220170200816
20220170200817
20220170200818
20220170200819
20220170200820
20220170200821
20220170200822
20220170200823
20220170200824
20220170200825
20220170200826
20220170200827
20220170200828
20220170200829
20220170200830
20220170200831
20220170200832
20220170200833
20220170200834
20220170200835
20220170200836
20220170200837
20220170200838
20220170200839
20220170200840
20220170200841
20220170200842
20220170200843
20220170200844
20220170200845
20220170200846
20220170200847
20220170200848
20220170200849
20220170200850
20220170200851
20220170200852
20220170200853
20220170200854
20220170200855
20220170200856
20220170200857
20220170200858
20220170200859
20220170200860
20220170200861
20220170200862
20220170200863
20220170200864
20220170200865
20220170200866
20220170200867
20220170200868
20220170200869
20220170200870
20220170200871
20220170200872
20220170200873
20220170200874
20220170200875
20220170200876
20220170200877
20220170200878
20220170200879
20220170200880
20220170200881
20220170200882
20220170200883
20220170200884
20220170200885
20220170200886
20220170200887
20220170200888
20220170200889
20220170200890
20220170200891
20220170200892
20220170200893
20220170200894
20220170200895
20220170200896
20220170200897
20220170200898
20220170200899
20220170200900